SUAME MUNICIPAL ASSEMBLY

2024 ANNUAL PROGRESS REPORT

ON THE IMPLEMENTATION OF THE 2022-2025 MTDP OF THE SUAME MUNICIPAL ASSEMBLY

JANUARY, 2025

Table of Contents

LIST OF ACRONYMS	3

LIST OF FIGURES	4

LIST OF TABLE	4

EXECUTIVE SUMMARY	5

CHAPTER ONE	6

GENERAL INTRODUCTION	6

1.2 Purpose of Monitoring and Evaluation (M&E) Report for 2024	10

MONITORING AND EVALUATION ACTIVITIES REPORT	17

2.0 Introduction	17

2.1 Physical Projects	17

2.2 Programmes/Non-Physical Activities	18

2.2 Update on Funding Sources and Expenditure	19

2. 3 Update on Indicators	23

2.4. UPDATE ON CRITICAL DEVELOPMENT AND POVERTY ISSUES	27

2.5 Evaluation Conducted, Findings and Recommendation	30

2.6 Participatory Monitoring and Evaluation	30

2.7 Update on Other Critical Development Indicators	30

Appendix 1: Staff Strengths of MMDAs	73

Appendix 2: Staff Strengths of MMDAs	73

Appendix 3 : PERFORMANCE OF NATIONAL CORE INDICATORS	73

APENDIX 4: PROJECT REGISTER	473

APENDIX 4b: PROGRAMME REGISTER	53

APENDIX 4a1: TOTAL NUMBER OF ACTIVE PROJECTS	761

APENDIX 4A2: DISTRIBUTION OF PHYSICAL PROJECTS AMONG DEPT OF THE ASSEMBLY	762

APENDIX 4A3: PROJECT ASSEMBLY, AGE ANALYSIS	73

APENDIX 4B: REPAIR AND MAINTENANCE OF EXISTING INFRASTRACTURE	73

APENDIX 5: UPDATE ON REVENUE SOURCE 	73

APENDIX 6A: EXPENDITURE	65

APENDIX 6B: CAPEX BUDGET PERFORMANCE ANALYSIS……………………………………................65

APENDIX 6C: CAPEX BUDGET ALLOCATION AND IMPLEMENTATION OF ACTIVE PROJECTS ...66

APENDIX 6D: COMMULATIVE CAPEX THROWN FORWARD AND MTBF ENVELOPE 2025-2027…………………………………………………………………………………………………………………….71

APENDIX 6E: AMOUNT OF CAPITAL ENVELPOPE SPENT ON ACTIVE PROJECTS…………………...71

APENDIX 6F: EXSTIMATED COST AND COST OVERRUN OF ACTIVE PROJECT……………………...72

APENDIX 7A: UPDATE AND CRITICAL DEVELOPMENT AND POVERTY ISSUES 2024……………...75

APENDIX 7B: STAFF STRENGTH OF MMDAs……………………………………………………….................76

APENDIX 7C: CAPACITY DEVELOPMENT…………………………………………………………..................77

APENDIX 7D: LOGISTICS ANALYSIS……………………………………………………………………………78

APENDIX 8:  UPDATE ON EVALUATION CONDUCTED…………………………………………...................79

APENDIX 9:  PARTICIPATORY M&E CONDUCTED…………………………………………………………..79

# LIST OF ACRONYMS

- CAPEX		-	Capital Expenditure

- CHPS 		-	Community Health Planning Service

- NGO		-	Non-Governmental Organization

- CBO		-	Community-Based Organizations

- MA 		-	Municipal Assembly

- DACF 		-	District Assembly Common Fund

- DDF 		-	District Development Facility

- GSCSP		-	Ghana Secondary Cities Support Programme

- MTDP		-	 Medium-Term Development Plan

- MPCU 		-           Municipal Planning & Co-coordinating Unit

- GOG		-	Government of Ghana

- IGF		-	Internally Generated Funds

- GSFP		-	Ghana School Feeding Programme

- MAG		-	Modernizing Agriculture in Ghana

- HIV 		-           Human Immune-Deficiency Virus

- JHS 		-           Junior High School

- SHS		-	Senior High School

- LEAP 		-	Livelihood Empowerment Against Poverty

- LED 		- 	Local Economic Development

- M&E 		-           Monitoring and Evaluation

- MP 		- 	Member of Parliament

- MSHAP		-	Multi Sectorial HIV and AIDS Programme

- MTDP 		-	Medium-Term Development Plan

- NDPC 		-	National Development Planning Commission

- NHIA 		-            National Health Insurance Authority

- NHIS 		- 	National Health Insurance Scheme

- NYEA		-	National Youth Employment Authority

- PM&E 		-           Participatory Monitoring and Evaluation

- PWD 		- 	Persons with Disability

- SMEs 		-	Small and Medium Scale Enterprises

- ANC		- 	Antenatal Care

- GHS		- 	Ghana Health Service

- ODF		-	Open Defecation Free

- GWC		-	Ghana Water Company

- SGBV		-	Sexual and Gender-Based Violence

- N/A		-	Not Applicable

# LIST OF FIGURES

1.0 annual action plan implemented by development dimensions.	15

1.1PROPROTION OF THE 2024 ANNUAL ACTION PLAN IMPLEMENTED 	16

2.1  project implementation performance per funding source	189

2.2 UPDATE OF REVENUE SOURCES	21

2.3 INTERNALLY GENERATED FUNDS PERFORMNACE BY REVENUE ITEMS	22

2.4 Update on eXPENDITURE by Economic CLASSIFICATIONS	23

2.5 FINANCIAL ASSISTANCE TO STUDENTS BY SEX	30

# LIST OF TABLES

1. 0 BROAD MUNICIPAL GOALS  AND OJBECTIVES	6

1.1 ANNUAL ACTION PLAN IMPLEMENTATION UNDER THE VARIOUS DEVELOPMENT DIMNESION 2023-2024	184

1.2 Proportion of 2024 Annual Action Plan Implemented …….	………………………………..16

2.0 projects implementation performance per the funding source	…..18

2.1 update on revenue source	Error! Bookmark not defined.…………………………………………………………………………………………20

2.2 INTERNALLY GENERATED FUNDS PER REVENUE ITEMS ……………………………………………………………22

2.3 UPDATE ON EXPENDITURE BY ECONOMIC CLASSIFICATION………………………………………………………23

2.4 MODULES UNDER NATIONAL YOUTH EMPLOYMET PROGRAMME …………………………………………………29

2.5 FINANCIAL ASSISTANCE TO STUDENTS BY SEX ………………………………………………………………………30

2.6 EVALUATIONS CONDUCTED ………………………………………………………………………………………………31

# EXECUTIVE SUMMARY

In fulfilment of the LI 2232, Suame Municipal Assembly prepared its 2024 Annual Progress Report based on National Development Framework dubbed “Agenda for Jobs II” to assess the level of implementation of the Medium-Term Development Policy Framework.

The report highlights status of the indicators and targets that was chosen for Monitoring, Evaluations, and the success of initiatives and programs put into achievement in 2024.  Critical development and poverty challenges, together with an update on disbursements according to funding sources, indicators and targets have also been outlined.

The report is organized in three chapters. Chapter One discusses the achievements made in the year and difficulties faced during the M&E process and challenges encountered in the process of preparing the Annual Progress Report.

The second chapter provides updates on assembly’s revenue and expenditures, critical development issues, evaluation conducted and participatory evaluation tools used. It also provides information on financing sources; disbursements, the Status of the indicators and targets, and crucial development challenges.

The Third and Final chapter provides the conclusions and recommendations touches on the most important concerns that need to be resolved and offers some suggestions for overcoming the obstacles.

A total number of Ninety-Five (95) programmes and projects were earmarked for implementation in the Composite Annual Action Plan for 2024, which was an extract from the Composite Annual Action Plan of the 2022-2025 MTDP. At the end of the year under review Ninety-One (91) of the projects and programmes representing 95.78% were implemented with 5 projects still on-going   while there were no projects that had been abandoned and 4 of the planned activities were not implemented.

In terms of revenue mobilization, the Assembly was able to realize a total revenue of Fifty-Two Million, One Hundred and Twelve Thousand Eight Hundred and Twenty-Four Ghana Cedis Forty-Nine Pesewas (GH₵ 52,112,824.49) out of its Budgeted Revenue of Eighty-Six Million Eight Hundred and Forty-Six Thousand Two Hundred and Thirty-Four Ghana Cedis Twenty-Five Pesewas (GH₵ 86,846,234.25) representing 60% of the annual projected composite revenue to finance its programmes and projects.

Total composite expenditure also summed up to Forty-Six Million, Two Hundred and Ninety-Five Thousand, Nine Hundred and Five Ghana Cedis, Sixty-Seven Pesewas (GH₵46,295,905.67) of annual projected composite expenditure. The Assembly recorded a surplus of Five Million, Eight Hundred and Sixteen Thousand Nine Hundred and Eighteen Ghana Cedis Eighty-Two Pesewas (GH₵5,816,918.82)

# CHAPTER ONE

## GENERAL INTRODUCTION

1.1 INTRODUCTION

The Suame Municipal Assembly prepared its 2024 Annual Progress Report in accordance with Legislative Instrument (LI 2232) with the view to demonstrate via evidence-based data the degree of programs and projects implementation under Agenda for Jobs II and that these interventions are having the intended effects on its citizens. As a result, the report shows the current state of the targets and the actual indicators that the stakeholders adopted. This report comes along with offering suggestions to assist in resolving all of the bottlenecks found in the preparation of the annual progress report and also tinted the shortcomings and obstacles in achieving the aims and objectives of the Policy Framework and DMTDPs.

Vision: The vision of the Assembly is "to be a pacesetter in local governance within a decentralized setting".

Mission: Suame Municipal Assembly exists to work towards improving the socio-economic development of its people through the utilization of the needed human and material resources for the provision of basic infrastructure to promote good governance and create a sustainable business-friendly environment for a resilient and safe Municipality.

Broad Municipal Goal: To create a human settlement that attracts, accelerates and sustains private sector development as well as meets the socio-economic needs of residents without compromising the ability of future generations to meet their developmental needs.

Table 1.0: The broad municipal specific goals and objectives indicator under each development dimension and the adopted strategies.

| DEVELOPMENT DIMENSION | MUNICIPAL DEVELOPMENT GOALS | MUNICIPAL ADOPTED OBJECTIVES | MUNICIPAL ADOPTED STRATEGIES |
| --- | --- | --- | --- |
| Economic Development Dimension | To augment revenue management and mobilization | To raise IGF's share of overall revenue from 8.5% from 2023 to 34% by 2025 | Provide the revenue collection officers with a rigorous and creative training program to increase their productivity and motivate them with incentive and bonuses to propel them to work diligently for the assembly |

|  | To support MSEs to improve productivity and quality of their products | To support 60 MSEs to improve the productivity and quality of their products by the end of 2025 | Educate and provide the SMEs in new technological methods of manufacturing their products and providing the enabling environment for their businesses to thrive. |
| --- | --- | --- | --- |
|  | To provide jobs for the unemployed Youth. | To provide jobs for unemployed Youth for at least 1000 by the end of 2025 | Prepare the youth with skills and innovative ideas to establish their own businesses and provide them with financial support and enabling environment. |
|  | To improve infrastructure for trading | To redevelop the existing market centres into ultra-modern satellite markets for effective trading | The municipality's current market centers should be transformed into state-of-the-art satellite markets and the route leading to the market should be redesigned for convenient access. |
|  | To update data management in business environment | To ascertain data on businesses to make informed decisions by management | To update the business register of all artisans and businesses within the municipality to ascertain their current information. |
| Social Development Dimension | To enhance inclusive and equitable access to and participation in quality education at all levels | To increase the school intake and improve the infrastructure base of the schools. | To provide the schools with at least 5,000 assorted school furniture and to construct additional classrooms to expand the student intake. |
|  | To ensure affordable, equitable, easily accessible, and Universal Health Coverage (UHC) | Improve access to universal health and reliable environmental sanitation services. | Adopted strategy is to furnish the newly constructed hospitals with advance equipment to enhance the activities. To educate and encourage community members to own their own toilet facilities. |
| Environment, Infrastructure and Human Settlement Development | To improve infrastructure in the area of sanitation | To increase access to sanitation by 96% by 2025 | Adopted strategy for the issue of sanitation is to build more household toilet and sensitization of citizens on proper waste management and disposal of E-waste within the Suame Magazine Enclave. |
|  | To improve the efficiency and effectiveness of road transport infrastructure and services | To ensure most inner roads are accessible by the end of 2025 | Adopted strategy is to rehabilitate and reshape existing poor road networks within the municipality and to provide a modern transport terminal using the DRIP machinery |
|  | Enhance the safety of people | Reduce occurrence of crime | Beef-up the security system and patrols in the municipality by providing the needed logistics to the security officers to intensify their patrol operations. |
|  | Minimize occurrence of environmentally related diseases in the municipality | Address recurrent devastating floods and environmental challenges | Educating the general public on newly environmental management practices and related diseases control mechanism |
|  | Reduce urban slums | Promote a sustainable, spatially integrated, balanced, and orderly development of human settlements | Provision of secure land tenure to residents that is safe from eviction, be it through land ownership or leasing. Partner with private estate developers to redevelop these slum areas |
|  | Construct accommodation for existing staff | Ensure decent office and residential accommodation | To increase productivity, improve employee retention and enhance job satisfaction |
|  |  |  | Access to a more diverse talent pool and enhance job satisfaction |
| Governance, Corruption and Public Accountability | To improve the performance of Sub-district Structures | To improve the capacity of Zonal Councils and Unit Committees | Promoting the process of development at the grass-root level towards the overall development of the municipality. |
|  | To promote peace and security in the municipality | To reduce accidents caused by these animals by 2025. To reduce the noise making to the acceptable limit by the end of 2025 | Strictly enforce the Assembly’s bye-laws as well as revising the local plans in the Municipality to accommodate churches and religious buildings to avoid conflict with residents. |
|  | To reduce the rate of flooding | To reduce the occurrence and impact of disasters within the municipality by the end of 2025 | Improving the storm drains and non-structural policies measures such as reducing development in flood-prone areas. |
| Emergency Planning and Response (Including Covid-19 Recovery Plan) | To mitigate the impact of disasters | To reduce the occurrence and impact of disasters within the municipality by the end of 2025 | Awareness creation, education, preparedness and adoption of zoning and land-use practices. Formation of disaster control teams within the various zonal councils |
| Implementation, Coordination, Monitoring and Evaluation | To improve coordination systems at the municipal level | To strengthen Co-ordination systems at the municipality | Understanding the terrain and collaboration with key stakeholders and getting support of leaders and the community. Engagement of all stakeholders in the decision-making process to strengthen the coordination system |

Source: 2022-2025 SMA, MTDP

The National Development Planning Commission (NDPC) with consent of relevant stakeholders developed a set of indicators that formed the basis for tracking and evaluating the performance and state of implementation of all the MMDAs.

This Annual Progress Report's goal is to provide a thorough summary of the progress made by the Suame Municipal Assembly in carrying out its 2024 AAP and Composite budget. The report also attempts to highlight problems that hindered the proper implementation of the 2024 AAP and potentially hinder the implementation of the Medium-Term Development Plan (MTDP) for 2022–2025 of the Assembly.

The report is the outcome of multiple stakeholder consultations, review meetings, and monitoring exercises. The report focuses on how successful policies, programs, initiatives, and strategies performed in respect to their stated indicators and targets.

A concise synopsis of the report, the state of the 2024 AAP and composite budget's execution, the goal of project monitoring and evaluation, and the procedures followed in producing this annual report are all covered in the first chapter.

Chapter two (2) captures the monitoring and evaluation (M&E) activities carried out during the year under review.

While chapter three (3) discusses the difficulties encountered throughout the implementation phase and offers suggestions for how to proceed in resolving the identified challenges.

### 1.2 Purpose of Monitoring and Evaluation (M&E) Report for 2024

An effective and efficient method for tracking the progress of projects and programs launched in the Municipality after the adoption of MTDP for the Suame Municipal Assembly has been established as a result of preparation of a monitoring and evaluation plan. In addition to the planned initiatives and programs, the Assembly also monitors the development of some of its key metrics and indicators unique to each municipality. The purpose of the yearly M&E exercise was to demonstrate the level of progress achieved in the 2024 and the third year of the 2022–2025 MTDP's implementation.

1.2.1 The specific objectives of the M&E exercise were as follows;

- To determine whether implemented programs and projects had achieved the intended impacts.

- To enhance the Municipality's effective resource mobilization and usage.

- To improve planning decisions in the future, it is necessary to recognize implementation process successes, obstacles, and failures.

- To review the effects of policies, programs, and projects.

- To improve the process of identifying successful programs that utilize customized interventions to address needs and challenges.

- To effectively communicate lessons learnt to improve future project management

- To ensure that programs and projects are carried out as planned.

- To satisfy the Assembly's mandatory requirement for the submission of yearly reports.

1.3 Summary of Achievements on the Implementation of the 2022-2025 MTDP

This document outlines the actions that the Assembly and its development partners took to implement its Composite Annual Action Plan (AAP, 2024). Suame Municipal Assembly based on a review of projects and programs implemented did very well by executing 95.78% of its 2024 AAP. Thus, the Assembly successfully completed 86 of the planned projects and Programmes. However, five (5) of the programs and projects are still on-going out of 91 implemented planned Programmes and projects set to be executed during the year.

Some achievements during the year under consideration for some sectors are explained below;

- Sanitation

- Construction of improved institutional and households’ toilets

Institutional sanitation received a major boost under the Greater Kumasi Metropolitan Area Sanitation and Water Project with completion of twelve (12) institutional improved sanitation facilities for eleven (11) schools. These facilities do not only come with the pit holes but additionally included girls changing rooms where girls can refresh themselves during their menstrual cycle instead for them to seek permission to go home only for some of them not returning to school which affect their academic performance compared to their male counterparts. These facilities also made provisions for disability friendly access as well as for female and male teachers. This contributes directly towards the Sustainable Development Goal 4 and 6 respectively. Under the same project a total of 2,390 low-income households were provided with improved household sanitation facilities at subsidized cost. These improved sanitation facilities have contributed towards the reduction in open defecation and reduced the likely occurrences of sanitation related diseases such as cholera, dysentery and diarrhea in the municipality thereby increasing the productivity capacity of the citizens.

The assembly also renovated 2No. 20-seater institutional toilets from its own resources for Kronum Cluster of schools while at the same time 1No. 10-seater water closet toilet was renovated for Bremang Cluster of schools from the assembly’s owned internally generated funds.

2. Construction of Reinforced Storm Drains

The Assembly was able to embark on extension of drainage system at Kronum Abouhia which has not only improved the sanitation in the community but also reduced occurrences of flooding in the community and its immediate environs.

3. Procurement of 2No. Cesspit Emptiers

With financial support from Ghana Secondary Cities Support Programme the assembly was able to procure 2No. cesspit emptiers with the view to improve sanitation in the municipality while at the same time increase its internally generated funds from the services of the cesspit emptiers.

- Market infrastructure

Kropo Market witnessed a major upgrade under the World Bank sponsored programmed dubbed Ghana Secondary Cities Support Programme as the old dilapidated structures were pulled down to make way for an Ultra-Modern Satellite Market with additional facilities such as Police Post, First Aid Block, modern water closet facilities, Meat shop, Bread kneading and corn mill shops. Similarly Old Suame Market also saw additional modern market facilities with 56 lockable shops constructed to boost trade in the municipality while at the same time increased the assembly’s internally generated funds to support its development agenda.

To boost trade and provide secured and convenient places for businessmen and women 1No. 2-storey twelve (12) unit lockable stores were constructed at Tarkwa Maakro aim at promoting local economic development by creating job opportunities for the people in the municipality.

Kronum Abuohia market was also completed and allocated to prospective users which are expected to improve the Internally Generated Funds and boost the economic activities within the project environs.

- Road Infrastructure

In order to reduce the traffic situation on the Suame-Kronum trunk road the upgrading of a number of inner-city roads within Tarkwa- Maakro and Suame enclave were undertaken to serve as alternative roads to minimize traffic congestion during the construction phase of the main Suame Interchange Project. The year also witnessed the completion of 10km surface dressing road on selected roads at Otumfour-Kyerase Road under partial Re-construction of Greater Kumasi roads.

Again, upgrading of 2.5km Link Road between Abuohia and Tigo Junction (Ohwim) under partial Re-construction of Greater Kumasi Roads was completed.

The Assembly witnessed the completion of 5km Asphaltic Overlay at Tarkwa-Maakro as part of the Local Roads Component of the Suame Interchange Project.

The Municipality benefited from the completion of 1.5km Asphaltic overlay link Road at Suame Magazine Japan House to Tafo – Cemetery under the Central Government Roads Initiative.

In the same vein, the year under consideration saw an award of 7.5km bitumen surface dressing at Abusuakruwa and Agogoso enclave under Ghana Secondary Cities Support Program (GSCSP). Lastly, the Assembly awarded a 600m road at Suame Ghana Education Link under Ghana Secondary Cities Support Program (GSCSP) to service the Suame Astroturf Park and Municipal Education Office.

- Revenue

Data available from the financial statement of the assembly indicate that at the end of December 2024, the Assembly was able to realize a total of Fifty-Two Million, One Hundred and Twelve Thousand Eight Hundred and Twenty-Four Ghana Cedis Forty Nine Pesewas (GH₵ 52,112,824.49) out of its Budgeted Revenue of Eighty-Six Million Eight Hundred and Forty-Six Thousand Two Hundred and Thirty-Four Ghana Cedis Twenty Five Pesewas (GH₵ 86,846,234.25) representing 60%.

This revenue under performance is as a result of the following reasons among others:

- Displacement of businesses along the main Suame-Kronum Trunk Road to make way for the construction of the Suame Interchange Project.

- There was no release of Urban Development Grant 5 funds under the Ghana Secondary Cities Support Programme as expected.

- The expected rent payment from Kropo and Old Suame Markets was not realized as most traders failed to fully pay their rents as scheduled. Some of the stores especially on the first floor have not been allocated as traders preferred stores on the ground floor which affected the assembly’s expected revenues for the year.

- Erratic flow in the release of the District Assemblies Common Funds also contributed to the low revenue mobilization.

Even though the Assembly did not meet its total revenue target, it was able to realize 92.29% out of its internally generated revenue target.

The implementation of the 2024 AAP under the Six (6) Development dimensions is highlighted in Table 1.2.

Considering the myriad of its development challenges certain development dimensions had a greater number of programmes and projects than the other dimensions. The Assembly attached much importance to some development dimensions depending on its priority.

Out of the six development dimensions, Environment, Infrastructure, and Human Settlement had the highest number of programmes and projects with fifty (41) programmes and projects undertaken. This was carried out with the intention of building schools, hospitals, and facilitating access to better and dependable environmental sanitation services. It was to increase access to sanitation services, accessibility to urban roads, address issues of devastating floods, among others in line with the achievement of Municipal set goals and objectives.

The Social dimension was ranked 2nd with 16 programmes and projects which sought to guaranteeing universal health coverage (UHC) and inexpensive, equitable, and conveniently accessible education, as well as improving inclusive and equitable access to and participation in quality education at all levels.

Governance Development Dimension had 10 programmes and projects implemented in 2024. As shown in Table 1.2. This dimension contributed to enhancing the effectiveness of sub-district structures and fostering peace and security within the Municipality.

The next Development Dimension was Economic which implemented 13 programmes and projects. The Economic Development Dimension helped to the improvement, mobilization and management of revenue, supporting SMEs to improve productivity and quality of their products, and providing jobs for the unemployed youth, among others as outlined in Table 1.2.

The fifth Development Dimension was Implementation, Coordination, Monitoring, and Evaluation Coordination which witnessed a total number of seven (7) programmes and projects. This was to strengthen coordination systems in the Municipality and to adhere to effective monitoring which seeks to ascertain both quantitative or qualitative factor or variable that provides a simple and reliable means to measure achievement, to reflect the changes connected to an intervention or to help assess the performance of a development actor and evaluation processes during and after the implementation of all the physical projects.

Emergency Planning and Response Development Dimension accounted for eight (8) projects and programmes implemented in the area of disaster mitigation and strategic management of all natural and man-made future occurrence of disaster.

In summary, a total number of Nine-One (91) of planned projects and programmes were executed in the 2024 AAP as against a total number of Ninety-Five (95) planned activities. Figure 1.0, 1.1 and Annex 2a further highlights a comparison of the performance of activities under the various development dimensions as implemented in 2023 and 2024 respectively

Figure 1.0: Annual Action Plan Implementation Under the Various Development  Dimension	Source: MPCU-Construct: Dec., 2024

Figure 1.1  Proportion of the Annual Action Plan Implemented

Source: MPCU Construct, 2024

1.4. Processes involved in the M&E and Difficulties Encouraged

1.4.1 The Process Involved

Suame Municipal Assembly used a participatory approach to gather data for the preparation of the 2024 Annual Progress Report.  In order to ensure that the report truly reflects the actual condition of affairs data was appropriately collected from the relevant departments and units.  Data collection templates were designed and reviewed at a validation meeting held on 6th January 2025. The heads of Departments were taken through the data collection templates with the view to ensure that they understand the templates and they were given two weeks to submit the populated templates. The data was validated at a second stakeholders’ session organized by the MPCU where all the Heads of Departments and Units were allowed to do PowerPoint presentation on the progress of the implementation of their respective departmental and units’ plans. After the validation of data, their reports were then incorporated into a drafted Annual Progress Report which was finalized.

As part of the process the various Stakeholders such as the User Departments, the Assembly members, the Unit Committee members, the Traditional Authorities, Civil Society Actors, Non-Governmental Organization Actors, and Trade Associations such as Ghana National Association of Garages were involved in the Monitoring of projects and Site meetings.

Data collected from the Departments, Units and Development Partners were scrutinized, analyzed which served as a draft report was finalized at another broad Stakeholder Consultative   validation session on 22nd January 2025 conducted by the MPCU with the aim of fine-tuning the report before onward submission to the National Development Planning Commission (NDPC) and the Regional Co-ordinating Council (RCC).

1.5 The Difficulties Encountered in doing M&E

In its efforts to conduct monitoring and evaluation exercises the under listed difficulties were encountered

- Untimely submission of data from some of the departments

- Inadequate staff strength and logistics for some of the departments also affect the conduct of monitoring and evaluation

- Low commitment by the political leadership on the importance of conducting monitoring and evaluation exercises.

- Insufficient and technical means to carry out frequent project assessments, monitor, and evaluate activities at all levels.

- Untimely submission of Departmental reports and other essential data required for conducting monitoring and evaluation.

- Inadequate and delayed release of funds affects the conduct of monitoring and evaluation exercise

CHAPTER TWO

## MONITORING AND EVALUATION ACTIVITIES REPORT

### 2.0 Introduction

This chapter discusses the monitoring and evaluation activities carried out during the year under review. The chapter also provides updates on funding sources and expenses during the year under consideration.  Moreover, the chapter provides updates on the Municipality's monitoring of the National Core Indicators as well as the Municipal Specific Indicators. In the same vein this chapter give assessments on participatory M&Es that were executed during the year under review along with a comprehensive update on critical development and poverty issues in the Municipality.

### 2.1 Physical Projects

This section gives an update on the physical projects implemented during the year. The update contains detailed information on each project, including the name description, location, contractor or consultant to projects, contract sum and funding sources.

The Assembly carried out Thirty-nine (37) physical projects in the year under review, as shown in Appendix 4a. This register shows the description of the projects, their locations, the contractors executing the projects, the contract sums, the source of funding and the various stages of completion of these projects.

There were seven (10) projects under the MP’s Common Fund, whilst the District Assemblies Common Fund funded eighteen (16) projects with the World Bank's Ghana Secondary Cities Support Program (GSCSP) funded five (5) projects, while six (6) of the projects were funded from the Internally Generated Funds (IGF).

The assembly continues to rely heavily on the external sources such as the District Assemblies Common Fund, MP’s Common Fund, HIPC (SIF), DACF-RFG and World Bank for most of its capital development where the assembly does not have any control over the quantum and the time of their releases.

The number of projects sponsored by the DACF was the highest, followed by those funded by the GSCSP, and DACF-RFG in that order. DACF-funded projects had the longest completion rate because of the delays in their releases which affects the completion rate as shown in Table 2.1 and Project Register at Appendix 4 a.

2.0 Project Implementation Performance per Funding Source

| Funding Source | Project Yet to Start | On-going Projects | Completed Projects | Abandoned Project | Total No. of Project |
| --- | --- | --- | --- | --- | --- |
| DACF | 0 | 2 | 14 | 0 | 16 |
| IGF | 0 | 0 | 6 | 0 | 6 |
| MPs CF | 0 | 3 | 7 | 0 | 10 |
| GSCSP | 0 | 0 | 5 | 0 | 5 |
| DACF-RFG | 0 | 0 | 0 | 0 | 0 |
| HIPC(SIF) | 0 | 0 | 0 | 0 | 0 |
| Total | 0 | 5 | 32 | 0 | 37 |

Source: MPCU-Construct Dec, 2024

Figure 2.0 Project Implementation

### 2.2 Programmes/Non-Physical Activities

In its efforts to raise the standard of living for the citizens, the Suame Municipal Assembly planned for 58 programs for its implementation for the year under review as depicted in Appendix 2 which detailed information on the description of the programme, level of implementation, budgeted amount, the actual disbursement and when the programme started and ended with pictorial evidences.

The majority of these programs served to enhance service delivery and in most cases protect the vulnerable residents, such as women, children, and people with disabilities, while other programs aimed to enhance the welfare and safety of the residents in order to safeguard the welfare and well-being of those who are most vulnerable in society and to facilitate their integration. Thus, several social protection initiatives were aggressively implemented.

### 2.2 Update on Funding Sources and Expenditure

#### 2.2.1 Updates on Revenue and External Funding Source

This section details out all monies from both external and internal sources as shown in Table 2.2.

During the year 2024, the Assembly estimated to collect a total revenue amount of Eighty-Six Million Eight Hundred and Forty-Six Thousand Two Hundred and Thirty-Four Ghana Cedis Twenty -Five Pesewas (GH₵ 86,846,234.25) but was able to mobilize a total revenue of Fifty-Two Million One Hundred and Twelve Thousand Eight Hundred and Twenty-Four Ghana Cedis Forty-Nine Pesewas (GH₵52,112,824.49) representing 60% a variance of GH₵34,733,409.76.

Ghana Secondary Cities Support Programme alone contributed enormously over (51.02%) of the total revenue amounting to Twenty Six Million Five Hundred and Ninety Thousand Three Hundred and Forty Six Ghana Cedis Eighty Six Pesewas(GH₵26,590,346.86) followed by the Internally Generated Fund (IGF) which brought in an amount of Seven Million Six Hundred and Four Thousand Four Hundred and Forty-Eight Ghana Cedis Twenty-Three Pesewas (GH₵7,604,448.23) representing (14.59%) followed closely by District Assembly Common Fund with an amount of Four Million Three Hundred and Twenty Eight Thousand Four Hundred and Twenty Nine Ghana Cedis Sixty Six Pesewas(GH₵4,328,429.66).

The Assembly was able to realize more revenue from rent as it has acquired landed properties and leased them out as rent. Thus, the construction of Abuohia Market and Tarkwa Market, redevelopment of the Old Suame Market and the Kropo Market fetching the Assembly with some revenue. Also, the release of funds from the MP’s Common Fund to support the Assembly’s subprojects earmarked under the Programme.

Table 2.1: Update on Revenue Sources

| Revenue sources | Estimates |  |  |  | Performance |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2021 | 2022 | 2023 | 2024 | 2021 | 2022 | 2023 | 2024 |
| DACF | 8,520,850.00 | 9,913,938.98 | 6,265,600.50 | 7,274,000.00 | 3,363,388.10 | 4,966,047.75 | 3,626,177.41 | 4,328,429.66 |
| DACF-RFG | 1,112,383.00 | 1,797,172.34 | 2,298,056.62 | 2,249,343.33 | 1,122,383.00 | 1,164,666.40 | - | 1,831,011.00 |
| MP’s CF | 1,589,782.84 | 3,315,270.88 | 538,712.55 | 3,915,000.00 | 294,652.07 | 461,029.15 | 1,029,657.72 | 2,149,214.41 |
| IGF | 3,387,850.00 | 3,512,900.00 | 5,050,000. | 8,200,969.52 | 2,230,287.57 | 2,185,937.17 | 3,438,712.29 | 7,604,448.23 |
| MSHAP/HIV | - | 49,569.69 | 50,000.00 | 50,000.00 | 5,191.46 | 42,264.30 | 5,624.08 | 33,744.48 |
| PWDs CF | 180,000.00 | 250,000.00 | 200,000.00 | 270,000.00 | 63,336.18 | 139,069.40 | 113,930.57 | 158,722.58 |
| GSCSP | 31,885,583.53 | 24,146,575.30 | 31,879,310.67 | 87,629,971.17 | 9,013,543.21 | - | 26,206,088.93 | 26,590,346.86 |
| MAG | 75,915.00 | 51,675.00 | 59,098.63 | - | - | 51,675.00 | 59,098.63 | - |
| GKMA | 10,547,565.99 | 156,000.00 | 150,000.00 | - | - | 50,000.00 | - | - |

Source: Finance Office, Dec. 2024, SMA

Figure 2.1 Update on Revenue Sources

2.2.2 Update on overall Revenue Performance

The Assembly's total revenue performance for 2024 was Fifty-Two Million One Hundred and Twelve Thousand Eight Hundred and Twenty-Four Ghana Cedis Forty-Nine Pesewas (GH¢ 52,112,824.49) a tremendous increase over 2023 amount of Thirty - Four Million Four Hundred and Seventy-Nine Thousand Two Hundred and Eighty Nine Ghana Cedis Sixty Three Pesewas (GH₵34,479,289.63). This represents 33.83% increase in revenue over the 2023 figure which can be partly attributed to the releases from Ghana Secondary Cities Support Programme and Rent from the stores.

It has been observed that total revenues over the three- year period have attained tremendous increase from GH¢ 9,060,689.17 in 2022 to GH¢ 52,112,824.49 in 2024.

On Internally Generated Funds mobilization the year under review recorded a total of Seven Million Six Hundred and Four Thousand Four Hundred and Forty- Eight Ghana Cedis Twenty- Three Pesewas (GH₵7,604,448.23) out of an estimated budget of Eight Million Two Hundred Thousand Nine Hundred and Sixty- Nine Ghana Cedis Fifty -Two Pesewas (GH₵8,200,969.52) representing 92.7 % achievement and 7.8% over the 2023 figure.

The internally generated revenue realized during the year accounted only 14.60% of the total revenue mobilized. This means that the Assembly’s chunk of the revenues came from the external sources where it has no control over the quantum and time of their releases.

Rent contributed more than half (64.69%) of the total internally generated funds of Four Million Nine Hundred and Nineteen Thousand Eight Hundred and Forty Two Ghana Cedis One Pesewa(GH₵4,919,842.01) followed closely by license which brought in  a total of  One Million Two Hundred and Nineteen Thousand Three Hundred and Ninety Seven Ghana Cedis Nineteen Pesewas (GH₵1,219,397.19) representing (16.03%) with fees bringing in a total revenue of Six Hundred and Ninety Six Thousand and Forty Four Hundred and Forty Eight Ghana Cedis Fifty Seven Pesewas (GH₵696,044.57). Fines was the least contributor towards the internally generated funds by raking in a total of Fifty- Four Thousand Six Hundred and Ninety Ghana Cedis (GH₵54,690.00) as illustrated in Table 2.3.

Table 2.2 Internally Generated Funds Performance by Revenue Items

| S/N | REVENUE HEAD | BUDGETED AMOUNT | ACTUAL | % |
| --- | --- | --- | --- | --- |
| 1 | Lands and royalties | 500,000.00 | 416,628.80 | 0.05 |
| 2 | Rates | 300,000.00 | 297,845.66 | 0.04 |
| 3 | Rent | 5,093,269.00 | 4,919,842.01 | 64.70 |
| 4 | License | 1,359,700.00 | 1,219,397.19 | 16.04 |
| 5 | Fees | 788,000.00 | 696,044.57 | 9.15 |
| 6 | Fines | 160,000.00 | 54,690.00 | 0.72 |
| Total |  | GH₵8,200,969.52 | GH₵7,604,448.23 | 92.73 |

Source: Dec 2024 Trial Balance, SMA

Figure 2.2 Internally Generated Funds Performance by Revenue Items

#### 2.2.3 Update on Disbursement/Expenditure

As illustrated in Table 2.4 the total composite expenditure for the 2024 fiscal year was Forty Six Million Two Hundred and Ninety Five Thousand Nine Hundred and Five Ghana Cedis Sixty Seven Pesewas (GH¢ 46,295,905.67) which were allocated across the three main categories namely compensation, goods and services and CAPEX.

The total expenditure figures indicate that in 2021 and 2022 the total expenditure figures remained almost the same. However there was a sharp rise in the total expenditures for the ensuing years 2023 and 2024 rising from Seventeen Million and Ninety Two Thousand Six Hundred and Sixty Six Ghana Cedis Sixty Seven Pesewas (GHC17,092,666.67) to Forty Six Million Two Hundred and Ninety Five Thousand Nine Hundred and Five Ghana Cedis Sixty Five Pesewas (GHC46,295,905.67)

Capex recorded the highest expenditure amounting to GH₵25,002,712.65 followed by Goods and Services with a total expenditure of GH₵11,139,053.15. Goods and Service was the least contributing budgetary item with an amount of GH₵10,178,939.87. A significant portion of the costs for goods and services came from the DACF, but the majority of the costs for assets came from the Ghana Secondary Cities Support Program of the World Bank.

Table 2.3: Update on Expenditure by Economic Classification

| Budget Items | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Released | Expenditure | Approved | Released | Expenditure | Approved | Released | Expenditure | Approved | Released | Expenditure |
| Compensation | 3,527,221.00 | 3, 443,583.53 | 3.443,583.54 | 4,702,862.81 | 4,550,579.04 | 4,550,579.04 | 7,473,261.89 | 6.869,360.39 | 6,869,360.39 | 11,602,389.71 | 10,1789,39.87 | 10,1789,39.87 |
| Goods and Services | 17,988,489.37 | 6,965,676.83 | 6,965,676.83 | 10,168,493.82 | 5,689,981.28 | 5,689,981.28 | 7,246,700.67 | 6,200,801.95 | 6,200,801.19 | 16,024,866.85 | 11,139,053.15 | 11,139,053.15 |
| CAPEX | 38,884,289.63 | 6,965,023.14 | 6,965,023.14 | 34,508,643.37 | 6,852,106.35 | 6,852,106.35 | 39,453,037.44 | 15,569,130.76 | 15,569,130.76 | 93,464,480.82 | 25,002,712.65 | 25,002,712.65 |
| Total | 60,400,000.00 | 17,374,283.50 | 17,374,283.50 | 49,380,000.00 | 17,092,666.67 | 17,092,666.67 | 54,173,000.00 | 21,769,932.71 | 28,639,292.34 | 121,091,737.38 | 36,141,765.80 | 46,295,905.67 |

Source: Finance Office, Dec. 2024, SMA

Figure 2.3 Update on Economic Expenditure

Source: MPCU Construct Dec. 2021, 2022, 2023, 2024

Figure 2.2 Update on GOG/ Grants

#### 2.2.2 Update on overall Revenue Performance

The Assembly's total revenue performance for 2023 was GH¢ 40,434,261.87 a sharp increase from it’s 2021 figure of GH¢ 19,159,068.56 . This represents 84.1% rise from the 2022 Actual revenue realized by the Assembly to 2023 Actual revenue the Assembly had, a situation that can be attributed to the inconsistent releases from GOG transfers/donor grant and subpar IGF performance. Consequently, the Assembly must take effective steps to improve its IGF performance in order to raise the IGF's share of total revenue from 75% to 95% by 2025.

### 2. 3 Update on Indicators

#### 2.3.1 National Core Indicators and Targets

The National Core Indicators, which were developed by the National Development Planning Commission (NDPC) in consultation with relevant Key Stakeholders, were to track the performance on the Projects and Programmes.  Inadequate funding and the delay in the release of the DACF and DDF had a major impact on the Assembly’s programs and projects executed. Data on the baseline, accomplishments, and targets for twenty-four (24) National core indicators and additional municipal-specific indicators are provided in Appendix 3.

a) Economic Development

In its efforts to achieve the municipal goal of creating a flourishing society and to enhance revenue mobilization and management, provide jobs for youngsters without work, this development dimension is very essential.

Production levels of major staple crops

Two major cereals namely maize and rice witnessed a decline in production from their 2023 production levels of 7.8 metric tons to 5.0 metric tons in 2024 and 4.8 metric tons to 2.0 metric tons due to longevity of drought and poor rainfall patterns as well as computing demand of lands for residential purposes. In another development cowpea, cassava and yam recorded a significant decline from the 2023 production levels as cassava production levels dropped from 8.6 metric tons to 7.0 metric tons while cowpea production declined more than half from 4.5 metric tons to 2.0 metric tons.

Two major crops namely plantain and groundnut recorded some significant increase in their production levels as they rose from 2.7 metric tons to 4.0 metric tons and from 2.8 metric tons to 3.5 metric tons respectively.

Animal Production

Cattle production in the year under review saw a slight increased from 4009 to 4128. At the same time goat and pig also witness some significant increase in population levels over the preceding year as indicated in appendix 3. Poultry production also recorded appreciable increase during the year under consideration as it rose from production level of 9891 in 2023 to 12,987 in 2024.

The continuous increase in number of cattle may be attributed to the presence of abattoir, which provides a means for farmers to sell their cattle. The general decline in farm animal production may have been caused by the strict enforcement of Municipal bye-laws that prohibit and restrict the rearing of livestock in open spaces.

Internal Revenue Mobilization

Revenue mobilization improved tremendously from the preceding year’s revenue as the Assembly was able to realize a total of Seven Million Six Hundred and Four Thousand Four Hundred and Forty-Eight Ghana Cedis Twenty-Three Pesewas (GH₵ 7,604,448.23) representing 92.73% of its revenue figure of Eight Million Two Hundred Thousand Ghana Cedis (GH₵8,200,000.00). This incredible Internally Generated Revenue Performance can be partly attributed to massive investments in market Redevelopment and Construction as well as procurement of Sanitary Trucks as shown in Appendix 3.

Job creation

The assembly in collaboration with Mastercard Foundation gave out a number of startups kits a benefitting a total of 186 entrepreneurs. Tailors and seamstresses constitute a sizable proportion of the beneficiaries. It is worth mentioned that out of the 186 beneficiaries 157 were females whilst only 29 were males.

The Municipal Assembly also supported a total of fourteen (14) people from different trade areas such as sewing, welding and hair dressing made up of eleven (11) females and three (3) males all aimed at creating business and reduce youth unemployment in the municipality. Under Ghana Jobs and Skills Project, fifteen entrepreneurs were financially supported with a grant amount of One Hundred and Sixty-Seven Thousand Three Hundred and Forty Ghana Cedis (GH₵ 167,340.00) made up of eleven (11) females and four (4) males.

A total of Eighty-Three (83) clients had the opportunity to formalize their businesses in order to transact businesses with the government and corporate institutions. Out of the total number, a higher proportion (56) were females whiles 27 were males.

b) Social Development

The Social Development component seeks to guarantee Universal Health Coverage (UHC) for all citizens at an affordable, equitable, and easily accessible cost, as well as to improve inclusive and equitable access to and participation in high-quality education at all levels.

Gender party index

Even though at all levels of education the Gender party index recorded increases over the preceding year’s ratios, they were not able to meet their set targets for the year.

Completion Rate

At all levels of education there have been persistence increase in the proportion of pupils who start school and able to complete at each level.

Pass Rate

The proportion of pupils and students who passed at both JHS and SHS levels rose from 96% to 100 and 80% to 95.5% respectively in 2021 but dropped to 95.5 and 55.1% in the year 2023. However, the data for the year was not readily available.

Functional Health Facilities

Functional private hospitals saw an increase from its 2023 figure of five (5) to six (6) during the year under review. In another development the number of functional clinics increased from four (4) to six (6) while the number of outreach points and CHPS Zones rose from twenty-four(24 to thirty-four (34) and six(6) to sixteen(16) respectively

Number of Birth by sex

During the year 2024 a total of four thousand Two Hundred and Nineteen (4,219) births were registered comprising 2,035 males and 2,184 females while a total of thirty (30) deaths were recorded made up of seventeen (17) males and thirteen (13) females.

Proportion of the population with access to Safe drinking water and improved sanitation services

A higher proportion of the population (98%) is said to have access to sustainable drinking water a slight increase from 97% in 2023 which may partly be attributed to the Greater Kumasi Metropolitan Area Sanitation and Water Project which supported low-income households to connect pipe-borne water to their houses at a highly subsidized cost.

The same situation cannot be said when it comes to access to improved sanitation services as a  number of the population with access to improved sanitation services stood at 84.6% as at the end of the year. This means that more efforts need to be put in place to improve households’ access to improved sanitation services in the foreseeing years. Thus, there is the need to consolidate the gains made under the World Bank’s Greater Kumasi Metropolitan Area Sanitation and Water Project in the Municipality.

Institutional Maternal Mortality Ratio

Institutional maternal mortality ratio recorded zero which needs to be sustained.

Malaria Case Fatality

Total of 9571 malaria case fatality was recorded during the year under review. The age group (31-59) recorded the highest cases of 4125 fellow by 6-30 age group which accounted for 2235.

c) Environment, Infrastructure and Human Settlement

The Environment, infrastructure and Human settlements Development Dimension which seeks to provide infrastructure while at the same time to promote orderly development in our communities saw some improvements during the year under consideration.

Road improvement

A total of 30 km paved roads was added to the existing paved roads during the year under review.  Thus, the Assembly witnessed an increase in improved condition of urban roads from 22.46km in 2022 to 30km in 2024. The increase in the length of paved roads within the Municipality as a result of the Central Government commitment to improve connectivity in the Municipality as well as the Assembly’s own commitment to improved connectivity.

d) Governance, Corruption and Public Accountability

The Governance, Corruption, and Public Accountability Dimension goal seeks to maintain a stable, united, and safe society.

Defilement cases have been persistently declining from 36 cases recorded in 2021 to 18 cases in 2024. Even though defilement cases have been declining over the years, it is worthy to note that all the victims are females which is a worrying concern as females are already vulnerable.

Armed robbery cases also dipped from 21 cases recorded in 2023 to 17 cases in 2024. More males are involved than their female counterparts. Murder cases remained the same over the one year period.

e) Emergency Planning and Response

The Emergency Planning and Response Dimension which focuses on Mitigation, Preparedness, Response and Recovery to both Natural and Man-made disasters. This Dimension also seeks to safeguard the health, safety, welfare and property of residents in communities and the Nation as a whole. Under this Dimension, the number of communities affected by disaster in 2024 reduced by 40% from its target figure of 10 to 3 cases.  But the number of people affected in terms of Domestic disaster was 45 as against 24 in 2024. This was as a result of intensive mass public education by NADMO and Ghana National Fire Service on disaster prevention and preparedness in the Municipality.

f) Implementation, Coordination, Monitoring, and Evaluation

The Implementation, Coordination, Monitoring and Evaluation Dimension is an accountability mechanism to ensure and report that activities are been delivered as planned in the Municipality. The Suame Municipal Assembly enhanced coordination, monitoring and evaluation mechanisms during the implementation of activities. The Assembly was able to implement a higher percentage (92.4%) of its programmes and projects in the Annual Action Plan. The Municipal Planning Co-ordination Unit embarked upon regular monitoring, site meetings and conducted town hall meeting to promote good governance and accountability. This not only helped to complete some projects which have been in the assembly’s books for long. The assembly also collaborated with other public institutions with the aim at ensuring a coordinated approach to development.

### 2.4. UPDATE ON CRITICAL DEVELOPMENT AND POVERTY ISSUES

#### 2.4.1 Free SHS Programme

The Municipality has only one (1) Senior High School with a total student population of 1,645 benefiting from the Free SHS Programme for the 2024/2025 academic year. Out of the total student population a sizable proportion of 1,014 are females whilst 631 are males. This shows that there are more females students in the Municipality as compared to their male counterparts. The Municipal Education Directorate could not provide information on allocation and actual receipts under the programme for the year under review.

#### 2.4.2 Ghana School Feeding Programme (GSFP)

A total of twenty-three (23) schools are currently benefiting from the Ghana School Feeding Programme with a total enrolment figure of 6,505, made up of 2,745 boys and 3,760 girls. This shows that there are more girls than boy’s counterparts in the municipality.

#### 2.4.3 Capitation Grants

As at the end of the year 2024, a total amount of GH₵ 50,379.16 was released for the Municipality as compared to 2023 figure of GH₵ 50,560.02. This shows a slight decrease of GH₵180.9 representing 0.36% reduction in the total amount received for 2024. Even though the reduction is insignificant it could affect the ultimate aim of improving education performance in the Municipality.

#### 2.4.4. National Health Insurance Scheme

The NHIS is a publicly funded healthcare systems established by the Government to provide equitable access and financial coverage for basic health care services to residents in Ghana. The NHIS subscription increased to 224,626 in 2024 from 217,332 in 2023. The municipality does not have its own Health Insurance Scheme office but operates under Manhyia Health Insurance Office. Data available at Manhyia Health Insurance Office indicate that active members as at December 2024 under the Scheme was 224,626 representing 3.36% a marginal increase over the 2023 active membership. During the year under review more females (122,835) renewed their membership cards compared to their male (74,746) counterparts. Out of the total membership female constitute 60.85% while males constitute 39.20% . Increase in the number of valid NHIS members, could be attributed to the mobile renewal system that has simplified the renewal system. The mobile renewal system continues to improve the re-enrolment fortunes of the National Health Insurance Scheme since the nationwide rollout.

#### 2.4.5 Livelihood Empowerment against Poverty (LEAP) Programme

In order to smoothen the daily consumption and nutritional level of extremely poor households, government through the MoGCSP paid five cycles of LEAP cash grants to 90 households of which all the beneficiaries are all females where a total amount of Ninety Six Thousand Two Hundred and Seventy Two Ghana Cedis (GH¢96,272.00) was disbursed to the beneficiaries.

#### 2.4.6 National Youth Employment Programme

The National Youth Employment Programme in the municipality runs 8 modules namely Youth in Skills Training, Community Protection Assistance, Prison Assistants, Community Health workers, BEAP, GARMENT, Security Assistant and Kitchen Assistant. These modules employ a total number of 199 youth in the Municipality. Details on the number per each module and their status are provided in Table 2.5.

Table 2.4:  Modules under National Youth Employment Programme

| No. | NAME OF MODULE | TOTAL NO. RECRUITED | NUMBER AT POST | NUMBER VACATED | NUMBER EXITED |
| --- | --- | --- | --- | --- | --- |
| 1. | Skills Training | 39 | 39 | 5 | 0 |
| 2. | Community Protection Assistance First Batch | 54 | 54 | 3 | 0 |
| 3. | Community Health Workers | 22 | 22 | 0 | 0 |
| 4. | Prison Assistants | 3 | 3 | 0 | 0 |
| 5. | BEAP | 63 | 63 | 0 | 0 |
| 6. | Security Assistant | 3 | 3 | 0 | 0 |
| 7. | Kitchen Assistant | 6 | 6 | 0 | 0 |
| 8. | Garment | 9 | 9 | 0 | 0 |
|  | Total | 199 | 199 | 8 | 0 |

Source: SMA NYA, DEC. 2024

2.4.7 Financial Assistance

A total of One Hundred and Ninety (190) students were given Financial Assistance during the year under review. 102 of the students representing 53.6% were females while 88 students representing 46.3% were males.  This clearly shows that the Assembly’s efforts at bringing the gender inequality gap in education is being vigorously pursued. The Assembly disbursed a total of Five Hundred and Fifty Four Thousand Four Hundred and Eighty One Ghana Cedis Sixty Six Pesewas (GH¢554,481.66)  as shown in Table 2.6.

2.6: Table 2.5: Financial Assistance to Students by Sex.

|  | Male | Female | Total |
| --- | --- | --- | --- |
| No. of Beneficiaries | 88 | 102 | 190 |
| Amount of Funds Disbursed | 177,240.83 | 377,240.83 | 554,481.66 |

Source: SMA Dec 2024 Trial Balance

Figure 2.4 Financial Assistance to Students by Sex

#### 2.4.8 Planting for Food and Jobs Programme

In 2024, the Department of Agriculture did not enroll any farmer onto the Planting for Food and Jobs Programme due to the fact that no funds were released to implement the programme. However, the Department of Agriculture continued their routine monitoring and supervision on the programme to ensure that the farmers continue to use improved technologies in carrying out their farming activities.

### 2.5 Evaluation Conducted, Findings and Recommendation

During the year under review, the Assembly conducted evaluations on the household and institutional improved sanitation facilities to assess the Relevance, Efficient, effectiveness and the impact of such facilities and as to whether the implemented projects had met its intended purpose for which they were initiated.

Table 2.6: Evaluation Conducted

| Name of Evaluation | Programme | Consultant/ Resource Persons Involved | Methodology used | Findings | Recommendations |
| --- | --- | --- | --- | --- | --- |
| Terminal evaluation | Greater Kumasi Metropolitan Area Sanitation and Water Project | Department of Planning, KNUST | Beneficiaries Survey | The project had improved contact hours for girl child and reduced Gender Based Sexual harassment and abuse among girl child | Future institutional toilet facilities should make provisions for girls changing rooms to cater for girls during their menstrual cycles to avoid a situation where girls go home during such periods and some never return to school thereby affecting the contact hours |

### 2.6 Participatory Monitoring and Evaluation

As part of its efforts to monitor projects progress, the Assembly adopted participatory monitoring and evaluation as a cost. Five projects were put through this process, and tools like community scores cards and citizen report cards were used to gather data on citizens’ perception with the chosen projects.

In order to prevent a situation where projects are completed but are not either used at all or are partially used, it was noted that the beneficiaries should be more involved in all stages of the project management.

During the monitoring of the projects the Team suggested that the Contractors should enforce the workers to adhere to wear personal protective equipment on site if available and also the contractor should mount sign post at the various sites for all on-going projects.

### 2.7 Update on Other Critical Development Indicators

Citizens engagement with the duty bearers

a) Town Hall Meetings and MCE Community Engagements

In pursuant to Section 55 of the Local Governance Act, 2016, (Act 936) and ensuring accountability and transparency, the Assembly held two Town Hall Meetings one in the first quarter of the year under review on the 28th March, 2024 which brought together a total of 55 people made up of 17 females and 38 males which touched on the performance on 2023 Annual Action Plan and Budget. The Second Town hall meeting was held on the 30th August, 2024 which attracted a total of 66 people made up of 21 females and 45 males which detailed out the number of projects and programmes the assembly has earmarked to be executed in its Draft 2025 Annual Action Plan and Composite Budget. It was also designed to get inputs and buy in from the citizens on the draft 2025 Annual Action Plan and Budget. The level of participation was not encouraging at all as the people failed to attend in their numbers at both meetings.

The purpose was to offer explanations on the performances of the assembly and to take feedback and inputs from relevant stakeholders regarding the implementation of its programmes and projects. It also created some level of ownership which is likely lead to sustainable development.

b) Municipal Chief Executive Engagements with the Citizens

To promote popular participation in the municipality and to improve the sense of ownership, the Municipal Chief Executive, embarked upon community visits with the aim at addressing some of the communities’ grievances and also to explain some of the government policies to the citizens for them to own the policies and to get their feedbacks on some of the government policies on their daily lives.  A total of eight (8) communities were visited where the Municipal Chief Executive interacted with the chiefs and the people not only to address their grievances but also to share with the people the various government policies, interventions and government flagship programmes being implemented by the government.

c) Celebration of 2024 Green Ghana Day

In its efforts to mitigate the negative effects of climate change the Suame Municipal Assembly joined hands with the rest of the country to celebrate 2024 Green Ghana Day held on 13th June 2024 where 1000 seedlings were received and planted. The climax of the celebration took place at the Forecourt of the Assembly where the Municipal Chief Executive Hon. Maxwell Ofosu Boakye together with the Hon. Member of Parliament for Suame with support from chiefs and his elders planted the seedlings and assured the people that they should nurture the trees they would plant.

Woman empowerment

The Suame Municipal Assembly having realized the importance of women empowerment through its Gender Desk collaborated with Department of Agriculture trained women on how to fortify gari with soyabeans and also trained women farmers on other income generating activities to augment their family income.

In another vein, Gender Desk Officer celebrated the World Menstrual Day  on 28th May 2024 where it was made known that the assembly with support from the Ministry of Sanitation and Water Resources under its Project Dubbed Greater Kumasi Metropolitan Sanitation and Water Project has constructed 12 gender friendly institutional toilet facilities where separate rooms have made exclusively for the girl child to change and refresh themselves during their menstrual cycles for 11 selected schools in the municipality.

The Gender Desk Officer has also been advocating for more women to be appointed as Government Appointees as all the elected members of the assembly are all men.

- Road Safety Activities/Programmes

- Road Safety Education and Vehicular Decongestion

Among the programmes on road safety programmes implemented in the municipality was creation of space for on street parking at Maakro, Road Patching and vehicular decongestion exercise on the main dual carriage road. The Transport Department in collaboration with Formed Police Unit, Departments and Units in the Assembly carried out certain mandates such as vehicular decongestion and education on road safety issues.

The Transport Department collaborated with Urban Roads Department to conduct Road Safety education for Transport Operators within the Municipality. Also, the Transport Department in collaboration with the Urbans Roads Department undertook vehicular decongestion exercise within the municipality which usually pose as a threat to the driving public and cause traffic congestions and sometimes lead to road accidents.

- Security and safety of the Citizens

The Works Department carried out maintenance works on mal-functional streetlights in the municipality with the view to improve visibility during night time and to improve security and to protect the citizens and aid night patrols by the security personnel.

Support for Culture and Tourism

To promote tourism and culture in the Municipality the assembly has been supporting financially the celebration of Akwasidae at Manhyia. During the year under review, the Assembly spent a total amount of Ten Thousand Ghana Cedis (GH₵10,000.00) in that direction to promote culture and safeguard Asante culture.

# CHAPTER THREE

## CONCLUSION AND THE WAY FORWARD

### 3.0 Introduction

The major development issues that were resolved and those that were not resolved during the implementation of the 2024 Composite Annual Action Plan are highlighted in this chapter. The chapter also suggests a number of recommendations in entering into another new year which will improve service delivery.

### 3.1 Summary of Key Issues Addressed and Those Yet to be addressed

The following key issues were addressed in the 2024 Composite Annual Action Plan which worth mentioning.

- All the assembly’s projects which were initiated since 2019 and were still running were completed due to prudent project and financial management.

- The Assembly took steps to continue some of the central government roads projects which had been abandoned due mainly to global economic crisis and its impact on the national economy.

- Some of the Middle Belt Development Authority abandoned projects were taken over by the assembly and were completed and put to use to serve their intended purposes.

- The Zonal councils were strengthened by training the members and staff to perform their statutory

Roles.

The Education and Health Departments were provided with spacious official accommodation to enhance their operations.

### 3.2 Key Issues Identified but not Addressed During the Implementation of the 2024 Composite Annual Action Plan

- The assembly could not complete and hand over the National Ambulance Service official accommodation which would be vigorously pursued in the coming year.

- The Assembly failed to construct official accommodation for the Zonal Councils.

- The assembly could not operationalize the Kwapra Health Centre even though it was able to renovate the main structure but it failed to procure hospital equipment to facilitate its functionality.

- The assembly is still grappling with its boundary disputes with Old Tafo, Afigya Kwabre South Municipal Assemblies and Kumasi Metropolitan Assembly.

### 3.3 Recommendations

The assembly will continue to make judicious use of its resources in order to address majority of its development targets.

It will also intensify its monitoring and supervision roles to ensure value for money

- There is the need to liaised with the Ghana Education Trust Fund(GetFund) Administrator to repackage all abandon GetFund projects in order to complete them.

- The administrator of District Assemblies Common Fund should ensure timely release of funds and increase its quantum.

- The assembly will continue to strengthen the zonal councils by providing them with the needed resources to enable them carry out their statutory mandates.

- The assembly will consolidate and sustain the gains under the Ghana Secondary Cities Support Programme and the Greater Kumasi Metropolitan Area Sanitation and Water Project.

- ICT would be continuously deployed in the coming years in the mobilization of revenue to minimize the leakages in revenue collection.

- The acquisition of an official vehicle for monitoring and evaluation exercise will facilitate regular program and initiative oversight and monitoring.

- It is important to post a substantive Head of Urban Roads Department as currently the Department does not have a substantive head.

- The Assembly should assist the Departments with logistics to carry out their programmes and activities.

In conclusion the assembly could have done better than it performed if the central government had released enough resources to enable it complete its projects and programmes. Hence in the ensuing years the assembly is determined to improve its internal revenue generation with the view to reduce its reliance on the central government as it has no control over the central government releases.

Annex 2a: Details on the Annual Action Plan Implementated

| S/N | Development Dimension | 2022 Baseline |  | 2023 |  | 2024 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Planned | Executed | Planned | Executed | Planned | Executed |
| 1. | Economic Development | 15 | 15 | 15 | 15 | 13 | 12 |
| 2. | Social Development | 17 | 15 | 15 | 15 | 16 | 15 |
| 3. | Environment, Infrastructure and Human Settlement | 31 | 31 | 39 | 30 | 41 | 41 |
| 4. | Governance, Corruption, and Public Accountability | 14 | 16 | 15 | 15 | 10 | 10 |
| 5. | Emergency Planning and Response | 6 | 6 | 6 | 6 | 8 | 8 |
| 6. | Implementation, Coordination Monitoring, and Evaluation | 8 | 8 | 8 | 8 | 7 | 5 |
|  | Total | 91 | 87 | 98 | 89 | 95 | 91 |

Source: MTDP-MPCU-SMA, Dec. 2024

Annex 2b:  Proportion of the DMTDP Implemented

| Indicators | Baseline 2021 | Actual (2022) | Target 2023(%) | Actual 2023(%) | Target 2024(%) | Actual 2024(%) |
| --- | --- | --- | --- | --- | --- | --- |
| The proportion of the annual action plan implemented by the end of the year | 92.6 | 95.6 | 100 | 90.8 | 100 | 95.78% |
| - Percentage of interventions Completed | 76.4 | 85.1 | 100 | 84.69 | 100 | 90.52% |
| (b) Percentage of interventions On-going | 15.7 | 14.9 | 30 | 6.12 | 0 | 5.26% |
| (c) Percentage of interventions abandoned | 0 | 0 | 0 | 0 | 0 | 0% |
| (d) Percentage of interventions yet to be initiated | 7.9 | 4.4 | 0 | 0 | 7 | 4.21% |
| (e) Percentage of interventions executed outside the plan | 0 | 0 | 0 | 0 | 0 | 0 |
| The proportion of the overall 2022-2025 MTDP implemented at the end of the year 2024 | 30 | 20.5 | 30 | 47.74 | 30% | 71.61% |

Source: MPCU-SMA, Dec., 2024

Annex 3: Performance of District Indicators

| No. | Indicator (Categorized by Development Dimension of Agenda for Jobs) |  |  |  |  |  |  |  | Baseline (2021) | Actual (2022) | Actual (2023) | Target (2024) | Actual (2024) | Key programmes undertaken | Challenges encountered in the year | Policy recommended |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | ECONOMIC DEVELOPMENT DIMENSION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. | Total output in agricultural production |  |  |  |  |  |  |  |  |  |  |  |  | Building the capacity of farmer-Based Organizations in agribusiness, record keeping was conducted. | Lack of motorbikes for AEAs. 2.Lack of funds. 3. poor rainfall pattern affected the production of legume and cereals drastically. | Means of Transport should be made available. Farmers were trained on improved livestock housing. Farmers were trained on improved technology. Ensure Early release of Funds. |
|  | - Maize (mt) |  |  |  |  |  |  |  | 7.3 | 5.0 | 7.8 | 8.3 | 5.0 |  |  |  |
|  | - Rice (milled) (mt) |  |  |  |  |  |  |  | 4.5 | 4.5 | 4.8 | 5.0 | 2.0 |  |  |  |
|  | - Cassava (mt) |  |  |  |  |  |  |  | 7.4 | 5.4 | 8.6 | 9.0 | 7.0 |  |  |  |
|  | - Yam (mt) |  |  |  |  |  |  |  | 3.7 | 5.5 | 4.0 | 5.0 | 4.5 |  |  |  |
|  | - Cocoyam (mt) |  |  |  |  |  |  |  | 3.2 | 4.8 | 4.5 | 5.0 | 4.0 |  |  |  |
|  | - Plantain (mt) |  |  |  |  |  |  |  | 2.2 | 5.0 | 2.7 | 4.0 | 3.5 |  |  |  |
|  | - Groundnut (mt) |  |  |  |  |  |  |  | 1.2 | 5.1 | 2.8 | 3.0 | 2.0 |  |  |  |
|  | - Cowpea |  |  |  |  |  |  |  | 1.4 | 4.7 | 4.5 | 5.0 | 3.5 |  |  |  |
|  | - Cattle (No.) |  |  |  |  |  |  |  | 2587 | 4215 | 4723 | 4000 | 4921 |  |  |  |
|  | - Sheep (No.) |  |  |  |  |  |  |  | 3596 | 3896 | 4009 | 4000 | 4128 |  |  |  |
|  | - Goat (No.) |  |  |  |  |  |  |  | 5240 | 5572 | 5973 | 4500 | 4897 |  |  |  |
|  | - Pig (No) |  |  |  |  |  |  |  | 1783 | 1329 | 2043 | 3500 | 3971 |  |  |  |
|  | - Poultry |  |  |  |  |  |  |  | 0 | 9427 | 9891 | 10000 | 12987 |  |  |  |
| 2. | Average productivity of selected crop |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Maize (mt) |  |  |  |  |  |  |  | Nil | 7.9 | 22.5 | 7.5 | 5.0 |  |  |  |
|  | - Rice (milled) (mt) |  |  |  |  |  |  |  | Nil | 4.8 | 11.9 | 4.8 | 2.0 |  |  |  |
|  | - Cassava (mt) |  |  |  |  |  |  |  | Nil | 8.6 | 8.1 | 8.6 | 7.0 |  |  |  |
|  | - Yam (mt) |  |  |  |  |  |  |  | Nil | 4.0 | 4.5 | 4.0 | 2.9 |  |  |  |
|  | - Cocoyam (mt) |  |  |  |  |  |  |  | Nil | 4.5 | 9 |  |  |  |  |  |
|  | - Plantain (mt) |  |  |  |  |  |  |  | Nil | 2.7 | 4.4 | 2.7 | 4.0 |  |  |  |
|  | - Groundnut (mt) |  |  |  |  |  |  |  | Nil | 2.8 | 6.8 | 2.8 | 3.5 |  |  |  |
|  | - Cowpea |  |  |  |  |  |  |  | Nil | 4.5 | 8.7 | 4.5 | 2.0 |  |  |  |
| 3. | Number of new industries established |  |  |  |  |  |  |  | 0 | 0 | 0 | 0 | 0 | MSME’s were assisted to formalize their Businesses Ghana Jobs and Skills Project beneficiaries were sensitized and trained on proper Business Management | Lack of Official vehicle to conduct follow-up on CAPBUSS Beneficiaries. | Means of Transport should be provided to ensure proper follow-ups. |
|  | - Agriculture |  |  |  |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | - Industry |  |  |  |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | - Service |  |  |  |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
| 4. | Number of new jobs created |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Agriculture |  |  |  |  |  |  |  | 0 | 0 | 0 | 0 | 0 | Recruited four (4) Prison Assistants 19 Youth under Ghana Jobs and Skills project were financially supported with startup tools and orientation. | Lack of funds. | Increase the quantum of grants for the prospective beneficiaries. |
|  | - Industry |  |  |  |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | - Service (Community policing, Garment, BEAP, Prison Assistant, security, kitchen Assistant, skills training and Community health workers) |  |  |  |  |  |  |  | 221 | 340 | 282 | 300 | 199 |  |  |  |
| 6 | Percentage change in IGF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | SOCIAL DEVELOPMENT DIMENSION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7. | Net Enrolment Ratio (Percentage) |  |  |  |  |  |  |  |  |  |  |  |  | In-service training for Basic School Head teacher on administrative management was organized. Monitoring of School Activities. Provision of improve sanitation facilities and school infrastructure. School feeding Programme continued to attract pupils | Inadequate Supply of Logistics and Funds for monitoring exercise Lack of infrastructure to accommodate pupils. Delay in paying the GSFP Caterers | The Inspectorate unit should intensify their supervisory and monitoring visit. Mock Examination were held for JHS Pupils Gender Responsive Infrastructure should be provided for remaining schools. Grant under GSFP should be paid on time. |
|  | - Kindergarten |  |  |  |  |  |  |  | 52.9% | 53.1% | 61.2% | 64% | 31.72% |  |  |  |
|  | - Primary |  |  |  |  |  |  |  | 55.2% | 56.3% | 63.2% | 72.6% | 57.29% |  |  |  |
|  | - JHS |  |  |  |  |  |  |  | 60.9% | 61.3% | 62.4% | 82% | 41.9% |  |  |  |
| 8. | Gender Parity Index |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Kindergarten |  |  |  |  |  |  |  | 1.07 | 1.0 | 0.99 | 1.09 | 1.03 |  |  |  |
|  | - Primary |  |  |  |  |  |  |  | 1.03 | 0.9 | 1.02 | 1.09 | 1.03 |  |  |  |
|  | - JHS |  |  |  |  |  |  |  | 1.02 | 0.9 | 1.07 | 2.0 | 1.09 |  |  |  |
|  | - SHS |  |  |  |  |  |  |  | 0.92 | 1.01 | 1.25 | 1.90 | 1.36 |  |  |  |
| 9. | Completion Rate (Percentage) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Kindergarten |  |  |  |  |  |  |  | 52.2% | 113.3% | 131% | 70% | 78% |  |  |  |
|  | - Primary |  |  |  |  |  |  |  | 61.3% | 124.2% | 129.1% | 70% | 88% |  |  |  |
|  | - JHS |  |  |  |  |  |  |  | 57.5% | 90.5% | 97.4% | 80% | 91% |  |  |  |
|  | - SHS |  |  |  |  |  |  |  | 18.3% | 97.6% | 98.3% | 35% | 40% |  |  |  |
| 10. |  |  | Pass rate |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - JHS |  |  |  |  |  |  |  | 96% | 100% | 95.5% | Not yet available | Not yet available |  |  |  |
|  | - SHS |  |  |  |  |  |  |  | 80% | 95.57% | 55.1% | Not yet available | Not yet available |  |  |  |
| 11 | Proportion of health facilities that are functional |  |  |  |  |  |  |  |  |  |  |  |  | Some logistics were provided for Health clinic | 1.No sample fridges to store samples such as Sputum, measles, YF and Meningitis 2. no freezer to store Ice packs at Kropo Market Facility 3. inadequate funds and fuels for planned activities and to run the office to send samples to Manhyia Hospital | 1. sample fridges should be available 2. Freezers should be made available to the Office so as to store Ice packs at Kropo Market. 3. Logistics should be provided for the health clinic on time to ensure smooth operation |
|  | - Government Hospital |  |  |  |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | - Private Hospital |  |  |  |  |  |  |  | 4 | 4 | 4 | 10 | 6 |  |  |  |
|  | - Clinic |  |  |  |  |  |  |  | 2 | 4 | 4 | 10 | 6 |  |  |  |
|  | - Maternity Home |  |  |  |  |  |  |  | 4 | 2 | 2 | 4 | 5 |  |  |  |
|  | - Out Reach Point |  |  |  |  |  |  |  | 20 | 24 | 24 | 40 | 34 |  |  |  |
|  | - Health Centre |  |  |  |  |  |  |  | 0 | 0 | 0 | 2 | 1 |  |  |  |
|  | - CHPS Zone |  |  |  |  |  |  |  | 5 | 6 | 6 | 20 | 16 |  |  |  |
| 12 |  |  |  |  | Prevalence of Malnutrition (institutional) |  |  |  |  |  |  |  |  |  |  |  |
|  | - Wasting |  |  |  |  |  |  |  | 0 | 0 | 0 | 0 | 4.3 |  | 1. Lack of weighing scale 2. lack of container clinics in the municipality. | 1. the Assembly should in the provision of weighing scales to enhance in smooth operation of the health facility in the municipality. 2. The Assembly should support in providing three (3) container clinics in the other places. |
|  | - Underweight |  |  |  |  |  |  |  | 0 | 0 | 0 | 0 | 10.51 |  |  |  |
|  | - Stunting |  |  |  |  |  |  |  | 0 | 0 | 0 | 0 | 5.5 |  |  |  |
|  | - Overweight |  |  |  |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
| 13 | Proportion of population with valid NHIS cards |  |  |  |  |  |  |  |  |  |  |  |  | 1.Stakeholders engagement 2. special registration exercise 3. indigent registration/ renewals 4. publicity campaign | 1.Budgetary constraints 2. lack of logistics | N/A |
|  | Total (by sex) |  |  |  |  |  |  | Male | 40.2% | 39.9% | 0 | 6.7% | 9.70% |  |  |  |
|  |  |  |  |  |  |  |  | Female | 59.8% | 60.6% | 0 | 8.3% | 10.14% |  |  |  |
|  | Indigents |  |  |  |  |  |  |  | 2.4% | 7.0% | 14.3% | 13.3% | 1.63% |  |  |  |
|  | Informal |  |  |  |  |  |  |  | 43.5% | 40.4% | 62.8% | 32% | 3.6% |  |  |  |
|  | Aged |  |  |  |  |  |  |  | 4.3% | 4.5% | 7.15% | 5.3% | 0.25% |  |  |  |
|  | Under 18 years |  |  |  |  |  |  |  | 41.4% | 40.0% | 63.9% | 7.2% | 8.39% |  |  |  |
|  | Pregnant women |  |  |  |  |  |  |  | 4.7% | 5.0% | 6.5% | 1% | 0.69% |  |  |  |
|  | Total Number of beneficiaries |  |  |  |  |  |  |  | 100% | 100% | N/A | 14.8% | 19.84% |  |  |  |
| 14 | Number of births and deaths registered (by sex) |  |  |  |  |  |  |  |  |  |  |  |  | Education on the existence of the department in the Municipal. | Lack of Official Vehicle to go undertake day-to-day activities. | Logistics should be provided |
|  | Birth Male Female Total Death Male Female Total |  |  |  |  |  |  |  | 1,788 | 2,345 | 10,627 | 2,000 | 2,035 |  |  |  |
|  |  |  |  |  |  |  |  |  | 1,614 | 2,945 | 10,973 | 2,000 | 2,184 |  |  |  |
|  |  |  |  |  |  |  |  |  | 3,402 | 5,290 | 21,600 | 4,000 | 4,219 |  |  |  |
|  |  |  |  |  |  |  |  |  | 0 0 0 | 0 0 0 | 0 0 0 | 0 0 0 | 17 13 30 |  |  |  |
| 15 | Percentage of population with sustainable access to safe drinking water services |  |  |  |  |  |  |  |  |  |  |  |  | Provision of subsidized water connection under GKMA project. | Irregular flow of water. | Quality and flow of water should be worked on |
|  | - Urban |  |  |  |  |  |  |  | 93% | 95% | 97% | 100% | 98% |  |  |  |
| 16 | Proportion of population with access to improved sanitation service |  |  |  |  |  |  |  |  |  |  |  |  | 1.GKMA households toilet facility sensitization. 2. user education on the GKMA household toilet facility | 1. inadequate space for the facility. 2. multiple landlords with litigation of property | 1. more engagement of landlords 2. enforcement of sanitary bye-laws |
|  | - Urban |  |  |  |  |  |  |  | 52% | 71% | 81.2% | 90.2% | 84.6% |  |  |  |
| 15. | Maternal mortality ratio (Institutional) |  |  |  |  |  |  |  | 0 | 0 | 0 | 0 | 0 | Educating Pregnant women and the masses on the need to sleep under Treated Mosquito net Educating Mothers on nutritional values for their wards. | Exorbitant fees charge by the Private health facilities | More public health facilities should be constructed. |
| 16. | Malaria Case Fatality (Institutional) |  |  |  |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | Sex |  |  |  |  | Male |  |  | 0 | 0 |  | 0 | 0 |  |  |  |
|  |  |  |  |  |  | Female |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  |  |  |  |  | Total |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | Age Group |  |  |  |  | 0-5 |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  |  |  |  |  | 6-30 |  |  | 0 | 0 | 0 | 0 | o |  |  |  |
|  |  |  |  |  |  | 31- 59 |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  |  |  |  |  | 60+ |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  |  |  |  |  | Total |  |  | 0 | 0 | 0 | 0 | o |  |  |  |
| 17 |  |  | Prevalence of malnutrition by phenomenon (institutional) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Number of recorded cases of child abuse |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Child trafficking |  |  | Male |  |  |  |  | 5 | 0 | 0 | 0 | 0 | Educating people on early marriage. | Some cultural practices and beliefs worked against the social vices. | Continuous conduct sensitization Programme. Improve income levels of some households. |
|  |  |  |  | Female |  |  |  |  | 7 | 0 | 0 | 0 | 0 |  |  |  |
|  |  |  |  | Total |  |  |  |  | 12 | 0 | 0 | 0 | 0 |  |  |  |
|  | Child Abuse |  |  | Male |  |  |  |  | 4 | 0 | 0 | 0 | 0 |  |  |  |
|  |  |  |  | Female |  |  |  |  | 6 | 0 | 0 | 0 | 0 |  |  |  |
|  |  |  |  | Total |  |  |  |  | 10 | 0 | 0 | 0 | 0 |  |  |  |
|  | Child Labor |  |  | Male |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  |  |  | Female |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  |  |  | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | Sexual Abuse |  |  | Male |  |  |  |  | 0 | 0 | 2 | 0 | 0 |  |  |  |
|  |  |  |  | Female |  |  |  |  | 0 | 0 | 0 | 0 | 1 |  |  |  |
|  |  |  |  | Total |  |  |  |  | 13 | 5 | 2 | 0 | 1 |  |  |  |
|  | Emotional abuse |  |  | Male |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  |  |  | Female |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  |  |  | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | Neglect |  |  | Male |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  |  |  | Female |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  |  |  | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | Early Marriage |  |  | Male |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  |  |  | Female |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  |  |  | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | Female Genital Mutilation |  |  | Male |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  |  |  | Female |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  |  |  | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | Family-Child Separation |  |  | Male |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  |  |  | Female |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  |  |  | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  | ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENT DEVELOPMENT DIMENSION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 19. |  |  | Percentage of road network in good condition (paved roads) (unpaved roads) Total |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Total |  |  |  |  |  |  |  | 22.46km | 22.46km | 22.46km | 40km | 30km | Asphaltic surface dressing, Periodic and Routine Maintenance | Abandoned projects. 2. lack of vehicles and equipment for the project 3. The number of staff is inadequate. | 1. the Assembly should e involved in the selection of roads. 2. Adequate staff should be recruited for the Department |
|  | - Urban |  |  |  |  |  |  |  | 22.46km | 22.46km | 22.46km | 40km | 30km |  |  |  |
| 20. |  |  | Percentage of communities covered by electricity within Suame Municipality |  |  |  |  |  |  |  |  |  |  | 1.network software programming for New Prepaid meters | Shortage of cables | Ability to learn the new program for the prepaid meters |
|  | - District |  |  |  |  |  |  |  | 100 | 100 | 100 | 100 | 100 |  |  |  |
|  | - Urban |  |  |  |  |  |  |  | 100 | 100 | 100 | 100 | 100 |  |  |  |
|  |  | GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY DIMENSION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 21. | Reported Cases of Crime |  |  |  |  |  |  |  |  |  |  |  |  | 1. Community patrols were conducted. | 1.Inadequate Official vehicle for Day and Night patrol 2. Inadequate funds for official duties. | More logistics should be provided for police patrol exercise. |
|  | Rape |  |  |  |  |  | Male |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  |  |  | Female |  | 13 | 5 | 4 | 0 | 6 |  |  |  |
|  | Armed Robbery |  |  |  |  |  | Male |  | 10 | 0 | 14 | 40 | 10 |  |  |  |
|  |  |  |  |  |  |  | Female |  | 13 | 3 | 7 | 40 | 7 |  |  |  |
|  | Defilement |  |  |  |  |  | Male |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  |  |  |  |  |  | Female |  | 36 | 28 | 24 | 0 | 18 |  |  |  |
|  | Murder |  |  |  |  |  | Male |  | 5 | 1 | 4 | 15 | 4 |  |  |  |
|  |  |  |  |  |  |  | Female |  | 7 | 1 | 0 | 0 | 0 |  |  |  |
|  | Stealing |  |  |  |  |  | Male |  | 95 |  | 160 | 20 | 15 |  |  |  |
|  |  |  |  |  |  |  | female |  | 55 |  | 97 | 20 | 2 |  |  |  |
|  | Drug Trafficking |  |  |  |  |  | Male |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  |  |  |  |  |  | Female |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | Peddling |  |  |  |  |  | Male |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  |  |  |  |  |  | Female |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | Domestic Violence |  |  |  |  |  | Male |  | 0 | 0 | 0 | 40 | 2 |  |  |  |
|  |  |  |  |  |  |  | Female |  | 128 | 121 | 0 | 40 | 15 |  |  |  |
|  |  | ERMENGENCY PLANNING AND RESPONSE DIMENSION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 22. | Number of communities affected by disaster Domestic Flood |  |  |  |  |  |  |  |  |  |  |  | 45 24 | The public was educated on disaster prevention and management. Early warning system signs were shared with the citizens especially those who lived at flood prone areas. | 1. Lack of Office equipment. 2. Lack of relief items to assist the needy in the course of an emergency. 3. Inadequate technical knowledge on disaster management. 4. Insufficient funds for financing the activities of the department. | More relief items should be released. Stringent compliance with the layouts. |
|  | - Floods |  |  |  |  |  |  |  | 8 8 | 5 | 3 | 10 | 3 |  |  |  |
|  | - Wind/Rain Storm |  |  |  |  |  |  |  |  | 5 | 0 | 0 | 0 |  |  |  |
| 23 |  |  | Proportion of population who have tested positive for COVID-19 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - District |  |  |  |  |  |  |  | 0.04 | 0.002 | 0 | 0 | 0 | 1.Educating the public on COVID-19 Protocols | Inadequate COVID 19 equipment’s. | Covid-19 relief items should be provided to the facilities |
|  | - Male |  |  |  |  |  |  |  | 0.02 | 0.00 | 0 | 0 | 0 |  |  |  |
|  | - Female |  |  |  |  |  |  |  | 0.02 | 0.00 | 0 | 0 | 0 |  |  |  |
| 24 | Percentage of Annual Action Plan Implemented |  |  |  |  |  |  |  | 92.6 | 97.8 | 97.8 | 100 | 92.2% | Quarterly MPCU Meetings on Annual Action Plan for 2024 | Lack of Official vehicle to contact other Department and Sectors for data. | More income generated activities should be conducted. Funds should be releases on time. |
|  |  | UPDATE ON MUNICIPAL SPECIFIC INDICATORS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. | Proportion of case workers trained in child protection and family welfare |  |  |  |  |  |  |  | 20 | 9 | 5 | 0 | 6 | 1. The Department supported Orphans and Vulnerable children in the Municipality. 2. Households were sensitized on Domestic Violence. 3. The Department conducted Income generated activities for PWD. 5. case worker trained. 6. child violence cases 7. registered LEAP Members on NHIS | 1. Inadequate funds for Official duties. 2. Inadequate logistics. | More income generated activities should be conducted. |
| 2. | Number of child violence cases benefitting from social welfare/social services |  |  |  |  |  |  |  | 15 | 0 | 0 | 26 | 32 |  |  |  |
| 3. | Number of children reached by social work/social services |  |  |  |  |  |  |  | 180 | 77 | 0 | 30 | 45 |  |  |  |
| 4. | Number of people reached with child protection and SGBV information |  |  |  |  |  |  |  | 1000 | 560 | 455 | 291 | 326 |  |  |  |
| 5. | Number of LEAP household members on NHIS |  |  |  |  |  |  |  | 215 | 286 | 195 | 252 | 252 |  |  |  |
| 6. | Number of households with adolescent girls benefiting from LEAP |  |  |  |  |  |  |  | 100 | 17 | 30 | 15 | 15 |  |  |  |
| 7. | Number of outreach visits to communities with LEAP households |  |  |  |  |  |  |  | 15 | 4 | 0 | 12 | 15 |  |  |  |
| 8. | Number of referrals received from GHS |  |  |  |  |  |  |  | 0 | 0 | 1 | 310 | 360 |  |  |  |
| 9. | Proportion of referrals receiving adequate follow-up |  |  |  |  |  |  |  | 0 | 0 | 2 | 7 | 10 |  |  |  |
| 10. | Number of DSWCD’s that have shared their MMDA’s LEAP Household data with both NHIS and GHS |  |  |  |  |  |  |  | 7 | 3 | 241 | 180 | 195 |  |  |  |
| 11. | Number of regional intersectoral monitoring visits conducted |  |  |  |  |  |  |  | 2 | 2 | 0 | 0 | 0 |  |  |  |
| 12. | Number of meetings organised to discuss integrated services |  |  |  |  |  |  |  | 2 | 2 | 0 | 0 | 0 |  |  |  |
| 13. | Number of girls reached by prevention and care services |  |  |  |  |  |  |  | 1792 | 807 | 402 | 430 | 500 |  |  |  |
| 14. | Number of CP/SGBV cases referred to other services and followed up |  |  |  |  |  |  |  | 70 | 9 | 2 | 4 | 10 |  |  |  |
| 15. | Number of NGOs, including RHCs, trained |  |  |  |  |  |  |  | 12 | 2 | 1 | 0 | 1 |  |  |  |
| 16. | Number of children placed in foster care |  |  |  |  |  |  |  | 17 | 0 | 2 | 0 | 0 |  |  |  |
| 17. | Proportion of population with access to basic drinking water sources |  |  |  |  |  |  |  | 93% | 95% | 95% | 100% | 95% |  |  |  |
| 18. | Proportion of population with access to improved sanitation services |  |  |  |  |  |  |  | 81% | 84% | 81% | 1000 | 924 |  |  |  |

Source: MPCU-SMA, Dec., 2024

Annex 4a: Project Register

| PROJECT DESCRIPTION |  | DEVELOPMENT DIMENSION | LOCATION | CONTRACTOR | CONTRACT SUM₵ | SOURCE OF FUNDING | DATE OF AWARD | DATE STARTED | EXPECTED DATE OF COMPLETION | EXPENDITURE TO DATE | OUTSTANDING BALANCE | IMPLEMENTATION STATUS |  | STRATEGIES TO IMPROVE PROJECT COMPLETION RATE | HOW CITIZENS WERE INVOLVED IN MONITORIN OF WORKS CONTRACT | REMARKS SUMMARRY ON LAND ACQUISITION AND RESETTLEMENT |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CODE | NAME |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | % | Pictures |  |  |  |
| 3113110 | CONSTRUCTION OF 2NO. MECHANIZED BOREHOLE WITHIN THE SUAME MUNICIPALITY | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | KRONUM/TAR KWA MAAKRO | M/S FOCUS 1 LIMITED/WKS DEP'T. | 149,985.75 | NHIS | 28/10/2024 | 18/11/2024 | 18/01/2025 | 0.00 | 149,985.75 | ON-GOING AT 20% COMPLETE |  | Site meeting Monitoring supervision | Key stakeholders were involved in site meeting and monitoring exercises | The Local chiefs and Elders lease lands to the Assembly |
| 2210603 | PAINTING OF 1NO. 2-STOREY CLINIC FACILITY AT SUAME MAGAZINE | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | SUAME MAGAZINE | M/S ADEHYEMAN STAR VENTURES | 149,961.00 | NHIS | 11/12/2024 | 16/12/2024 | 16/02/2025 | 149,961.00 | 0.00 | COMPLETED AND IN USE |  | Projects already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3111251 | CONSTRUCTION OF FENCE WALL FOR KWAPRA AT KWAPRA | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | KWAPRA | M/S FOCUS 1 LIMITED/WKS DEP'T. | 449,979.00 | NHIS | 28/10/2024 | 31/10/2024 | 31/01/2025 | 384,531.00 | 65,448.00 | ON-GOING AT 75% COMPLETE |  |  | Key stakeholders were involved in site meeting and monitoring exercises | The Local chiefs and Elders lease lands to the Assembly |
| 3111354 | CONSTRUCTION OF 9NO. LOCKABLE STORES AT ABOUHIA MARKET | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | ABUOHIA | M/S KAOBA COMPANY LIMITED/WKS DEP'T. | 549,886.40 | DDF | 28/10/2024 | 31/10/2024 | 31/03/2025 | 501,601.40 | 48,285.00 | ON-GOING AT 80% COMPLETE |  |  | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3111353 | REHAILITATION OF 1NO.10-SEATER W/C TOILET FACILITY AT BREMAN M/A SCH. | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | BREMAN CLUSTER OF SCHOOLS | M/S KAOBA COMPANY LIMITED/WKS DEP'T. | 219,341.00 | IGF | 28/10/2024 | 31/10/2024 | 31/12/2024 | 219,341.00 | 0.00 | COMPLETED AND IN USE |  | Projects already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3111201 | DEMOLITION AND RECONSTRUCTION OF BEDROOMS FACILITY FOR THE CONSTRUCTION VAMED HOSPITAL ACCESS ROAD AT ANOMAGYE | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | ANOMNAGYE | M/S ADEHYEMAN STAR VENTURES/WKS DEP'T. | 250,608.50 | IGF | 28/10/2024 | 31/10/2024 | 31/01/2025 | 250,608.50 | 0.00 | COMPLETED AND IN USE |  | Projects already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 2210603 | PAINTING OF 3-STOREY SUAME MUNICIPAL ASSEMBLY'S OFFICE BLOCK | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | SUAME | M/S KAOBA COMPANY LIMITED/WKS DEP'T. | 350,165.00 | IGF | 13/8/2024 | 16/08/2024 | 16/9/2024 | 350,165.00 | 0.00 | COMPLETED AND IN USE |  | Projects already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3111201 | REHABLITATION OF KWAPRA HEALTH CENTER | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | KWAPRA | M/S KAOBA COMPANY LIMITED/WKS DEP'T. | 543,592.86 | DDF | 13/08/2024 | 16/08/2024 | 16/11/2024 | 516,412.17 | 27,180.69 | COMPLETED AND HANDED OVER |  | Projects already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3111354 | CONSTRUCTION OF 60NO. LOCKABLE SHOPS FOR SUAME MUNICIPAL ASSEMBLY AT OLD SUAME MARKET | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | OLD SUAME | M/S AS AFRIMP GHANA LIMITED/AVANGARDE DESIGN SERVICES | 5,045,735.75 | GSCSP | 4/3/2024 | 4/4/2024 | 22/11/2024 | 5,061,639.08 | 15,903.33 | COMPLETED AND IN USE |  | Projects already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3111354 | CONSTRUCTION OF STORE TYPE ‘E1’ 40, STORE TYPE ‘D1’ 32 UNIT, EXTERNAL WORKS AND 110M OF ROAD WITH DRAINAGE SYSTEM | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | KROPO | M/S ALHAJI AND MADINA COMPANY LIMITED/AVANGARDE DESIGN SERVICES | 8,232,994.13 | GSCSP |  |  |  | 7,511,625.01 | 721,369.12 | COMPLETED AND IN USE |  | Projects already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3111354 | CONSTRUCTION OF POLICE POST/FIRST AID BLOCK AND CONSTRUCTION OF STORE TYPE ‘C7’ | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | KROPO | GREAT NABIL LIMITED/AVANGARDE DESIGN SERVICES | 4,796,919.62 | GSCSP | 25/07/2022 | 22/09/2022 | 22/07/2023 | 4,359,367.66 | 437,551.96 | COMPLETED AND IN USE |  | Projects already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3111354 | CONSTRUCTION OF 2-STOREY 8NO. STORES AND WASHROOM, 4-UNITS (40NO). STALL (TYPE E), 1UNITS (20NO). STALL (TYPE C), 1-UNIT (5NO). STALL (TYPE D), DEMOLITION AND EXTERNAL WORKS | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | KROPO | M/S ELIFERT LIMITED/AVANGARDE DESIGN SERVICES | 4,360,128.18 | GSCSP | 25/07/2022 | 22/09/2022 | 22/07/2023 | 3,990,607.93 | 369,520.25 | COMPLETED AND IN USE |  | Projects already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3111353 | REHABLITATION OF 1NO. 20-SEATER WC FACILITY AT KRONUM CLUSTER OF SCHOOLS | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | KRONUM | M/S ADEHYEMAN STAR VENTURES/WKS DEP'T. | 199,952.00 | IGF | 15/12/2023 | 20/12/2023 | 21/03/2024 | 199,952.00 | 0.00 | COMPLETED AND IN USE |  | Projects already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3111353 | REHABLITATION OF 1NO. 20-SEATER WC FACILITY AT KRONUM CLUSTER OF SCHOOLS | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | KRONUM | M/S KAOBA COMPANY LIMITED/WKS DEP'T. | 198,202.00 | IGF | 15/12/2023 | 20/12/2023 | 21/03/2024 | 198,202.00 | 0.00 | COMPLETED AND IN USE |  | Projects already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3111363 | CONSTRUCTION OF 6M HEIGHT X 0.45M WIDTH: 48M LONG RETAINING WALL | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | OLD SUAME | M/S JUSTIDAN GLOBAL LTD./WKS DEP'T. | 543,592.86 | DDF | 7/11/2023 | 14/11/2023 | 14/04/2024 | 555,320.70 | -11,727.84 | COMPLETED AND IN USE |  | Projects already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 2210616 | EVACUATION OF REFUSE HEAP AT KRONUM CLUSTER OF SCHOOLS | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | KRONUM | M/S KAOBA COMPANY LIMITED/WKS DEP'T. | 193,982.00 | IGF | 30/10/2023 | 3/1/2024 | 12/1/2024 | 193,982.00 | 0.00 | COMPLETED |  | Projects already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3111356 | CONSTRUCTION OF 1NO. 3-UNITS CLASSROOM BLOCK WITH OFFICES AND STORES | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | BREMAN CLUSTER OF SCHOOLS | M/S DD CARAVAN VENTURES/WKS DEP'T. | 702,703.50 | DACF (MP) | 13/03/2024 | 14/03/2024 | 14/08/2024 | 557,887.39 | 144,816.11 | ON-GOING AT 80% COMPLETE |  |  | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3111256 | CONSTRUCTION OF 1NO. 3-STOREY 12-UNIT CLASSROOM BLOCK WITH ANCILLARY FACILITIES & 16 SEATER WC TOILET FACILITY (PHASE 1 - 6UNIT CLASSROOM BLOCK WITH ANCILLARY FACILITIES & 8SEATER WC TOILET FACILITY OF THE GROUND FLOOR) AT ST, JOSEPH PRIMARY SCHOOL, ANOMANGYE NKWANTA | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | ANOMNAGYE NKWANTA | M/S FOCUS 1 LIMITED/WKS DEP'T. | 648,013.30 | DACF (MP) | 30/06/2020 | 26/08/2020 | 26/02/2021 | 600,930.20 | 47,083.10 | COMPLETED AND IN USE |  | Projects already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3111255 | CONSTRUCTION OF 1NO. 2-STOREY OFFICES AND LIBRARY & ICT CENTRE WITH MECHANIZED BOREHOLE AT SUAME M/A PRIMARY SCHOOL (PHASE 1 - GROUND FLOOR) | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | SUAME | M/S MAKOSSY ENTERPRISE/EWKS DEP'T. | 854,257.06 | DACF | 8/8/2019 | 21/08/2019 | 21/02/2020 | 813,528.15 | 40,728.91 | COMPLETED AND IN USE |  | Projects already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3111256 | CONSTRUCTION OF 1NO. 2-STOREY 6-UNIT CLASSROOM BLOCK WITH ANCILLARY FACILITIES AT BREMAN | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | SUAME | M/S ELIFERT LIMITED/WKS DEP'T. | 749,775.87 | DACF (MP) | 23/04/2021 | 28/05/2021 | 28/02/2022 | 639,550.04 | 110,225.83 | COMPLETED AND IN USE |  | Projects already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3111353 | CONSTRUCTION OF 1NO. 12-SEATER WATER CLOSET TOILET FACILITY WITH 1NO. MECHANIZED BOREHOLE AT BREMAN NKONTWIMA SATELITE MARKET | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | KRONUM | M/S BOASAGEM CO. LTD,/WKS DEP'T. | 438,324.85 | DDF | 8/8/2019 | 15/10/2022 | 15/04/2023 | 438,324.85 | 0.00 | COMPLETED AND IN USE |  | Projects already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3111354 | CONSTRUCTION OF 8NO. LOCKABLE STORES, 50NO. OPEN SHEDS AND 10SEATER WC TOILET FACILITY FOR PROPOSED MARKET AT ABOUHIA | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | ABUOHIA | M/S ALHAJI AND MADINA CO. LTD./WKS DEP'T. | 818,198.82 | DDF | 23/04/2021 | 28/05/2021 | 28/11/2021 | 744,457.43 | 73,741.39 | COMPLETED AND IN USE |  | Projects already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3111256 | CONSTRUCTION OF 1NO. 2-STOREY GYMNASIUM AND LIBRARY & ICT CENTRE WITH MECHANIZED BOREHOLE AT MAAKRO M/A SCHOOL (PHASE 1 - GROUND FLOOR) | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | MAAKRO | M/S MAKOSSY ENTERPRISRE/WKS DEP'T. | 803,847.08 | DACF | 8/8/2019 | 21/08/2019 | 21/02/2020 | 727,282.62 | 38,278.03 | COMPLETED AND HANDED OVER |  | Projects already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3111255 | CONSTRUCTION OF 1NO. 2-STOREY AMBULANCE BAY WITH OFFICES AT TARKWA-MAAKRO | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | TARKWAMAAKRO | M/S DIVINE DESTINY LTD./WKS DEP'T. | 899,896.91 | DACF | 5/12/2022 | 21/12/2022 | 21/09/2023 | 854,530.58 | 45,366.33 | COMPLETED AND HANDED OVER |  | Projects already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3111354 | CONSTRUCTION OF 1NO. 2-STOREY 12-UNITS LOCKABLE STORES AT TARKWA-MAAKRO | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | TARKWAMAAKRO | M/S SAVVY SOLUTIONS LTD. | 1,112,299.86 | DDF | 5/12/2022 | 21/12/2022 | 21/09/2023 | 1,056,567.39 | 55,732.47 | COMPLETED AND HANDED OVER |  | Projects already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3111255 | CONSTRUCTION OF 1NO. 3-STOREY MUNICIPAL EDUCATION DIRECTORATE AT SUAME M/A PRIMARY SCHOOL (PHASE 2 - FIRST FLOOR) | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | SUAME | M/S GEOBENOP ENTERPRISE/WKS DEP'T. | 549,043.56 | DACF | 31/12/2020 | 28/01/2021 | 28/06/2021 | 398,119.73 | 150,923.83 | COMPLETED AND IN USE |  | Projects already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3111256 | CONSTRUCTION OF 1NO. 3-STOREY 18-UNIT CLASSROOM BLOCK WITH ANCILLARY FACILITIES & 24-SEATER WC TOILET FACILITES (PHASE 1- 6 UNIT CLASSROOM BLOCK WITH ANCILLARY FACILITIES & 8-SEATER WC TOILET FACILITIES AT THE GROUND FLOOR AT ADADIEM M/A PRIMARY SCHOOL | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | ADADIEM | M/S FOCUS 1 LIMITED/WKS DEP'T. | 979,326.81 | DACF (MP) | 30/06/2020 | 26/08/2020 | 26/02/2021 | 146,899.02 | 832,427.79 | ON-GOING AT 75% COMPLETE |  |  | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 31112214 | PROCURE AND MAINTAIN STREETLIGHTS | ENVIRONMENT/INFRASTRUCURE AND HUMAN SETTLEMENT | MUNICIPALITY WIDE |  | 99,400.00 | DACF | 12/03/24 | 15/03/24 | 29/03/24 | 99,400.00 | 0.00 | Procured and maintained |  | Supervision and monitoring | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 2210603 | MAINTAIN OFFICE BUILDING, FURNITURE AND VEHICLES | GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY |  |  |  | DACF |  |  |  |  |  | Office building maintained |  | Supervision and maintenance | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 2210102 | PROCURE 75NO. CONFERENCE HALL CHAIRS AND FITTING | GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY | SUAME | DD CARAVAN | 99,750.00 | GSCSP |  | 15/04/24 | 03/05/24 | 99,750.00 | 0.00 |  |  | Periodic maintenace | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 2210610 | DESILT CHOCKED DRAINS AND STREAMS | EMERGENCY PLANNING AND RESPONSE | Acheampongmine Ngradaa Stream (magazine BB Area) Municipality wide Kwapra Area | Kaobo Const. Co. Ltd. Adehyeman Star Ventures Adehyeman Star Ventures Messrs D.D. Caravan | 499,979.00 | DACF/IGF |  | 28/10/24 | 28/01/24 | 499,979.00 | 0.00 |  |  | Already completed | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3113103 | PROCURE AND DISTRIBUTE 500NO. DUAL DESK SCHOOL FURNITURE | GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY | MUNICIPALITY WIDE | DD CARAVAN | 197,000.00 | DACF |  | 17/05/24 | 17/06/24 | 197,000.55 | 0.00 |  |  | Periodic supervision and maintenance | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 3112206 | PROCURE 1NO. GENERATOR PLANT | GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY | SUAME | KWANTIES ENTERPRISE | 101,000.00 | DACF |  | 9/02/24 | 23/02/24 | 101,000.00 | 0.00 |  |  | Already in use | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 2210112 | PROCURE OFFICE CURTAINS | IMPLEMENTATION, COORDINATION, MONITORING AND EVALUATION | SUAME | AFRAKOMA 89 ENTERPRISE | 36,499.60 | DACF | 28/06/24 | 2/07/24 | 2/08/24 | 36,499.60 | 0.00 |  |  | Already in use | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 2210108 | CONSTRUCTION OF FENCE WALL FOR KWAPRA HEALTH CENTRE | IMPLEMENTATION, COORDINATION, MONITORING AND EVALUATION | KWAPRA | FOCUS 1 LIMITED | 449,979.00 | MP’S /NHIA |  |  |  | 449,979.00 | 0.00 |  |  | Already in use | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |
| 2210108 | PROCURE OF PORTLAND CEMENT | IMPLEMENTATION, COORDINATION, MONITORING AND EVALUATION | SUAME | DD CARAVAN | 399,840.00 | MP’s/DACF |  | 28/10/2024 | 28/11/2024 | 399,840.00 | 0.00 |  |  | Procured | Key stakeholders were involved in site meeting and monitoring exercise | The Local chiefs and Elders lease lands to the Assembly |

Source: MPCU-SMA, Dec., 2024

Annex 4a.1: Total Number of Active Projects

| Development Dimension | Physical Projects in the Municipality |  |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Roll over projects from previous years |  |  | Approved new projects introduced in the year |  |  |  |
|  | 2022 | 2023 | 2024 | 2022 | 2023 | 2024 |  |
| Economic Development | 3 | 10 | 12 | 0 | 6 | 3 | 34 |
| Social Development | 11 | 10 | 14 | 0 | 1 | 11 | 47 |
| Environment/Infrastructure/Human Settlement | - | - | - | - | - |  | - |
| Governance/Corruption/ Public Accountability | 3 | 2 | 5 | 0 | 1 | 2 | 13 |
| Emergency | 4 | 8 | 12 | 0 | 0 |  | 24 |
| ICME | 3 | 1 | - | 0 |  |  | 4 |
| Total | 24 | 31 | 39 | 0 | 8 | 16 | 122 |

Source: MPCU-SMA, Dec., 2024

Annex 4a. 2: Distribution of Physical Projects among Departments of the Assemblies

| Departments | No. of projects |  | Total | Collaborating MDA |
| --- | --- | --- | --- | --- |
|  | Rollover | New |  |  |
| Works | 13 | 16 | 29 | Education Department, Central Administration, Health Department |
| Urban Road | 1 | - | 1 | Works Department, Central Administration Department |

Source: MPCU-SMA, Dec., 2024

Annex 4a. 3: Project age analysis

| Project Age | No. of Projects | Time Over runs (in years and months) | Cost Overruns | Completion Status |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Average completion Rate (%) | Highest (%) | Least (%) |
| Projects that are 20years but less than 24 years | NIL | NIL | NIL | NIL | NIL | NIL |
| Projects that are 11 years but less than 18 years | NIL | NIL | NIL | NIL | NIL | NIL |
| Projects that are 10 years but less than 11 years | NIL | NIL | NIL | NIL | NIL | NIL |
| Projects that are 9 years but less than 10 years | NIL | NIL | NIL | NIL | NIL | NIL |
| Projects that are 8 years but less than 9 years | NIL | NIL | NIL | NIL | NIL | NIL |
| Projects that are 7 years but less than 8 years | NIL | NIL | NIL | NIL | NIL | NIL |
| Projects that are 6 years but less than 7 years | NIL | NIL | NIL | NIL | NIL | NIL |
| Projects that are 5years but less than 6years | NIL | NIL | NIL | NIL | NIL | NIL |
| Projects that are 4years but less than 5years | NIL | NIL | NIL | NIL | NIL | NIL |
| Projects that are 3years but less than 4years | NIL | NIL | NIL | NIL | NIL | NIL |
| Projects that are 2years but less than 3years | 7 | NIL | NIL | NIL | NIL | NIL |
| Projects that are 1years but less than 2years | 3 | NIL | NIL | NIL | NIL | NIL |
| Projects that are 0years but less than 1year | 20 | - | - | 50% | 100% | 20% |
| Total projects | 30 |  |  |  |  |  |

Source: MPCU-SMA, Dec., 2024

Annex 4b: Repair and Maintenance of Existing Infrastructure

| Asset/infrastructure | Location | Type of Maintenance | Estimated Cost | Actual release | Gap | Expenditure | Recommendation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Suame Magazine Clinic | Suame – Magazine | Renovation | 149,961.00 | 149,961.00 | 0.00 | 149,961.00 | Implemented |
| Breman Toilet Facility | Breman | Renovation | 219,341.00 | 219,341.00 | 0.00 | 219,341.00 | Implemented |
| Suame Municipal Assembly Office Block | Suame | Painting | 350,165.00 | 350,165.00 | 0.00 | 350,165.00 | Implemented |
| Kwapra Health Center | Kwapra | Rehabilitation | 543,592.86 |  | 27,180.69 | 516,412.17 | Implemented |
| 1No. 20-Seater W/C Facility | Kronum M/A | Rehabilitation | 199,952.00 | 199,952.00 | 0.00 | 199,952.00 | implemented |
| 1No. 20-Seater W/C Facility | Kronum M/A | Rehabilitation | 198,202.00 | 198,202.00 | 0.00 | 198,202.00 | Implemented |
| Evacuation of Refuse Heap at Kronum Cluster of Schools | Kronum M/A | Evacuation works | 193,982.00 | 193,982.00 | 0.00 | 193,982.00 | Implemented |

Source: MPCU-SMA, Dec., 2024

Annex 4c: Programme Register

| Programme Description |  | Development Dimension of Policy Framework | Amount Involved Sum GH₵ | Source of Funding | Date started | Expected date of Completion | Expenditure to Date | Outstanding Balance | Implementation Status |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | (%) | Pictures (if any) |  |
| ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |
| 1.Prepare 2025 composite budget and gazette FFR |  | Economic | 65,000.00 | DACF | 1/07/24 | 31/10/24 | 125,000.00 | 35,000.00 | 100% |  | implemented |
| 2. Prepare RIAP |  | Economic | 15,000.00 | DACF |  |  | 11,380.00 | Nil |  |  | Implemented |
| 3.Organize meetings with private business associations |  | Economic | 60,000.00 | GSCSP | 19/12/24 | 19/12/24 | 40,000.00 | NIL | 100% |  | Implemented |
| 4.Assist MSMEs to access business development Service and finance |  | Economic | 15,000.00 | DACF/GOG/GEA | 03/01/24 | 03/01/24 | 13,850.00 | NIL | 100% |  | Implemented |
| 5.Organize business development service training |  | Economic | 15,000.00 | DACF | 10/01/24 | 10/01/24 | 1000 | NIL | 100% |  | Implemented |
| 6.Conduct follow-up visits on CAPBUSS beneficiaries |  | Economic | 10,000.00 | DACF | - | - | - | - | - |  | Not Implemented |
| 7.Assist MSMEs to formalize their businesses |  | Economic | 15,000.00 | Client | 04/01/24 | 04/01/24 | 120.00 | NIL | 100% |  | Implemented |
| 8.Organize Farmers Day Celebration |  | Economic | 150,000.00 | DACF | 08/11/24 | 08/11/24 | 130,000.00 | NIL | 100% |  | Implemented |
| 9.Conduct Home and farm visits |  | Economic | 28,000.00 | DACF | 21/01/24 | 31/12/24 | No Fund | NIL | 100% |  | Implemented |
| 10.Organize demonstration on maize, taro and vegetables |  | Economic | 7,598.67 | DACF | 1/03/24 12/12/24 | 1/03/24 12/12/24 | No Fund | NIL | 100% |  | Implemented |
| 11.Conduct Technical Review meetings |  | Economic | 5,000.00 | DACF | 27/03/24 19/06/24 26/09/24 1/11/24 | 27/03/24 19/06/24 26/09/24 1/11/24 | No Fund | NIL | 100% |  | Implemented |
| 12.Sensitize livestock farmers on new technologies |  | Economic | 5,000.00 | DACF | 08/08/24 1/11/24 | 08/08/24 1/11/24 | No Fund | NIL | 100% |  | Implemented |
| 13.Conduct Surveillance and Management of Diseases and Pests |  | Economic | 16,200.00 | DACF | 28/03/24 11/12/24 | 28/03/24 11/12/24 | No Fund | NIL | 100% |  | Implemented |
|  | SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |
| 14.Organize My First Day at School |  | Social | 12,000.00 | DACF | 10/09/24 | 10/09/24 | 9,000.00 | NIL | 100% |  | Implemented |
| 15.Support Sports and other cultural activities |  | Social | 25,000.00 | DACF | 30/10/24 1/11/24 | 20/12/24 1/11/24 | 20,000.00 | NIL | 100% |  | Implemented |
| 16.Support Akwasidae Celebration |  | Social | 30,000.00 | DACF | 24/03/24 | 08/12/24 | 28,000.00 | NIL | 100% |  | Implemented |
| 17.Provide Scholarship for 200 students (120 girls and 80 boys) |  | Social | 172,058.87 | DACF | Jan 2024 | Dec 2024 | 662,981.65 | NIL | 100 |  | Implemented |
| 18.Celebrate 67th Independence Day |  | Social | 100,000.00 | DACF | 6/03/24 | 06/03/24 | 96,272.00 | NIL | 100% |  | Implemented |
| 19.Undertake LEAP programmes |  | Social | 2,000.00 | GOG | 12/08/24 | 12/08/24 | 1,060.00 | NIL |  |  | Implemented |
| 20.Support 30 female PWDs with income generating activities |  | Social | 5,000.00 | DACF | 16/05/24 | 16/05/24 | 111,500.00 | NIL | 100% |  | Implemented |
| 21.Organise programmes for PWDs and link them to NHIS |  | Social | 3,000.00 | DACF | 2/01/24 | 31/12/24 | 2,000.00 | NIL | 100% |  | Implemented |
| 22.Conduct social enquiry into child custody and juvenile in conflict with the law and sensitize young girls on pMenstrual Hygiene |  | Social | 2,000.00 | DACF | 28/05/24 | 28/05/24 09/08/24 | 8,500.00 | NIL | 100% |  | Implemented |
| 23.Conduct Mass Education on Conflict Management |  | Social | 2,500.00 | DACF | 29/05/24 | 30/05 /24 | 2,000.00 | NIL | 100% |  | Implemented |
| 24.Organize health Education on HIV/AIDS, Malaria and Provide support for PLHIV |  | Social | 20,000.00 | DACF/MSHAP | 06/03/24 05/06/24 23/06/24 29/11/24 19/12/24 | 06/03/24 05/06/24 23/06/24 29/11/24 19/12/24 | 33,744.48 | NIL | 100% |  | Implemented |
| 25.Build capacity for health workers on Data reporting, on Family Planning, Malaria Case management and Adolescent Health |  | Social | 28,000.00 | DACF/GOG | 18/07/24 | 22/07/24 |  | N/A |  |  | Implemented |
| 26.Conduct Surveillance service on health facilities |  | Social | 10,000.00 | GOG | 03/07/24 19/09/24 | 07/07/24 21/09/24 |  | NIL | 100% |  | Implemented |
| 27.Organize quarterly health committee meetings |  | Social | 10,000.00 | DACF | 26/03/24 19/06/24 09/10/24 | 26/03/24 19/06/24 09/10/23 | 5,000.00 | NIL | 100% |  | Implemented |
| 28.Conduct Investigation into background of children forced into early marriages and alms begging |  | Social | 3,000.00 | DACF/GOG | 15/01/24 | 17/01/24 | 600 | NIL | 100 |  | Implemented |
| 29.Organise talk sessions on child abuse, labour and domestic violence in 4 schools |  | Social | 2,000.00 | DACF/GOG | 05/06/24 11/09/24 | 06/06/24 12/09/24 | No Fund | NIL | 100 |  | Implemented |
| 30.Organise Annual Performance Review meeting with stakeholders |  | Social | 5,000.00 | DACF/GOG | 20/02/24 | 20/02/24 | 4,925.00 | N/A | 100% |  | Implemented |
| ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENT DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |
| 32.Support the promotion of Household bio-digester toilets |  | Environment, infrastructure and human settlement | 50,000.00 | GKMA | 21/01/24 | 31/12/24 | No Fund | NILL | 100% |  | Implemented |
| 33.Conduct clean up exercises including clearing of weeds from road median |  | Environment, infrastructure and human settlement | 20,000.00 | DACF | 22/01/24 | 22/01/24 | 27,100 | NILL | 100% |  | Implemented |
| 34.Conduct food vendors screening exercise |  | Environment, infrastructure and human settlement | 10,000.00 | DACF | 24/04/24 | 24/06/24 | 26,000.00 | NIL | 100% |  | Implemented |
| 35.Organize Technical and Spatial Planning Committee Meetings |  | Environment, infrastructure and human settlement | 24,000.00 | DACF | 2/01/24 | 31/12/24 | 20,000 | NIL | 100% |  | Implemented |
| 36.Organize public education on proper waste management |  | Environment, infrastructure and human settlement | 10,000.00 | DACF | 02/04/24 | 02/04/24 | 24,000.00 | NIL | 100% |  | Implemented |
| 37.Advocate for more women in government appointees |  | Environment, infrastructure and human settlement | 5,000.00 | DACF | 14/02/25 | 14/02/25 | No funds | N/A |  |  | Implemented |
| 38.Organize weekly site inspections on development permits |  | Environment, infrastructure and human settlement | 7,000.00 | DACF | 2/01/24 | 31/12/24 | - | NIL | 100% |  | Implemented |
| 39.Revise 2 planning schemes |  | Environment, infrastructure and human settlement | 30,000.00 | DACF |  |  |  | NIL | 100% |  | Implemented |
| 40.Observe Green Ghana with Tree planting exercise |  | Environment, infrastructure, human settlement | 30,000.00 | DACF | 07/06/24 | 07/06/24 |  | NIL | 100% |  | Implemented |
| 41.Prepare ARAP |  | Governance | 300,000.00 | GSCSP |  |  |  |  |  |  |  |
| 42.Organize 1-Day training on the protocols of the service for new entrants |  | Governance | 20,000.00 | DACF | 26/04/24 | 26/04/24 | 10,000.00 | NIL | 100% |  | Implemented |
| GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY |  |  |  |  |  |  |  |  |  |  |  |
| 31.Support more girls to venture into Science, Mathematics and Engineering |  | Governance | 5,000.00 | DACF |  | 25/03/24 | 4000.00 | N/A | 100% |  | Implemented |
| 43.Conduct Road safety exercise for transport operators |  | Governance | 60,000.00 | DACF | 20/12/24 | 20/12/24 | No Fund | NIL | 100% |  | Implemented |
| 44.Undertake vehicular decongestion exercise |  | Governance | 50,000.00 | DACF | 2/08/24 14/08/24 | 2/08/24 14/08/24 | No Fund | Assembly 6,000 | 100% |  | Implemented |
| 45.Create Space for Street parking |  | Implementation, coordination monitoring and evaluation | 50,000.00 |  |  |  |  |  |  |  | Not implemented |
| 46.Conduct sensitization exercise at selected fuel stations |  | Governance | 2,300.00 | DACF | 26/04/24 | 26/04/24 | 10,000.00 | NIL | 100% |  | Implemented |
| 47.Organise at least Two Town Halls meetings on plan and budget implementation |  | Governance | 100,000.00 | DACF | 23/05/24 | 23/05/24 | 108,850 | NIL | 100% |  | Implemented |
| 48.Organise community engagements with MCE |  | Governance | 125,000.00 | DACF | 7/05/24 13/05/24 15/05/24 | 7/05/24 13/05/24 15/0524 | 38,000.00 | Nil | 100 |  | Implemented |
| EMERGENCY PLANNING AND RESPONSE |  |  |  |  |  |  |  |  |  |  |  |
| 49.Conducted inspection on Gas, Fuel Station |  | Environment, human settlement | 1,000.00 | DACF | 26/04/24 | 26/04/24 | 1000.00 | NIL | 100% |  | Implemented |
| 50.Procure and distribute 500 No. Dual Desk School Furniture |  | Environment, human settlement | 130,000.00 | DACF/IGF |  | 04/06/24 | 197,000.00 | NIL | 100 |  | Implemented |
| 51. Prepare Municipal Master Drainage Plan |  | Implementation, coordination, monitoring and evaluation | 150,000.00 | GSCSP | 26/04/24 | 26/04/24 | 150,000.00 | NIL | 100% |  | Completed |
| 52.Organize public education for artisans on effects of carbon emission |  | Implementation, coordination, monitoring and evaluation | 40,000.000 | GSCSP | 19/12/24 | 19/12/24 | 40,500.00 | NIL | 100% |  | Completed |
| 53.Organise Education on early warning systems for flood prone areas |  | Implementation, coordination, monitoring and evaluation | 8,000.00 | DACF | 26/04/24 | 26/04/24 | 10,000.00 | NIL | 100% |  | Completed |
| 54.Organise Public Education on flood and fire outbreaks |  | Implementation, coordination, monitoring and evaluation | 7,000.00 | DACF | 2/07/24 | 26/04/24 |  | NIL | 100% |  | Completed |
| 55. Conduct Flood Hazard Assessment and prepare Flood Hazard Map |  | Implementation, coordination, monitoring and evaluation | 80,000.00 | GSCSP | N/A | N/A | N/A | N/A | 0% |  | Not implemented |
| IMPLEMENTATION, COORDINATION, MONITORING AND EVALUATION |  |  |  |  |  |  |  |  |  |  |  |
| 56. Organize Municipal Education Oversight Committee meetings and monitoring |  | Implementation, coordination, monitoring and evaluation | 8,000.00 | DACF | 27/03/24 25/06/24 24/09/24 10/12/24 | 27/03/24 25/06/24 24/09/24 10/12/24 | 8,000.00 | NIL | 100% |  | Implemented |
| 57.Hold inter-service collaboration meetings |  | Environment, human settlement | 15,000.00 | DACF | 30/04/24 | 07/02/24 | 10,050.00 | N/A | 100% |  | Implemented |
| 58. Conduct Monitoring and Evaluation on projects |  | Implementation | 463,859.89 | DACF/GSCSP | 17/12/24 24/09/24 26/06/24 27/03/24 | 18/12/24 26/09/24 28/06/24 29/03/24 | 77,996.25 | N/A | 100% |  | Implemented |

Source: MPCU-SMA, Dec., 2024

Annex 5: Update on Revenue Sources

| Revenue sources | Estimates |  |  |  | Performance |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2021 | 2022 | 2023 | 2024 | 2021 | 2022 | 2023 | 2024 |
| COMPENSATION |  |  |  |  |  |  |  | 9,356,907.27 |
| DACF | 8,520,850.00 | 9,913,938.98 | 6,265,600.50 | 7,274,000.00 | 3,363,388.10 | 4,966,047.75 | 3,626,177.41 | 4,328,429.66 |
| DACF-RFG | 1,112,383.00 | 1,797,172.34 | 2,298,056.62 | 2,249,343.33 | 1,122,383.00 | 1,164,666.40 | - | 1,831,011.00 |
| MP’s CF | 1,589,782.84 | 3,315,270.88 | 538,712.55 | 3,915,000.00 | 294,652.07 | 461,029.15 | 1,029,657.72 | 2,149,214.41 |
| IGF | 3,387,850.00 | 3,512,900.00 | 5,050,000. | 8,200,969.52 | 2,230,287.57 | 2,185,937.17 | 3,438,712.29 | 7,604,448.23 |
| MSHAP/HIV | - | 49,569.69 | 50,000.00 | 50,000.00 | 5,191.46 | 42,264.30 | 5,624.08 | 33,744.48 |
| PWDs CF | 180,000.00 | 250,000.00 | 200,000.00 | 270,000.00 | 63,336.18 | 139,069.40 | 113,930.57 | 158,722.58 |
| GSCSP | - | - | - | - | - | - | - | 26,590,346.86 |
| HIPC(SIF-MP) | - | - | - | - | - | - | - | 60,000.00 |
| MAG | 75,915.00 | 51,675.00 | 59,098.63 | - | - | 51,675.00 | 59,098.63 | - |
| GKMA | 10,547,565.99 | 156,000.00 | 150,000.00 | - | - | 50,000.00 | - | - |
| TOTAL |  |  |  |  |  |  |  | 52,112,824.49 |

Source: Finance Office, Dec. 2024, SMA

Annex 6A: Update on Expenditure

| Budget Items | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Released | Expenditure | Approved | Released | Expenditure | Approved | Released | Expenditure | Approved | Released | Expenditure |
| Compensation | 3,527,221.00 | 3, 443,583.53 | 3.443,583.54 | 4,702,862.81 | 4,550,579.04 | 4,550,579.04 | 7,473,261.89 | 6.869,360.39 | 6,869,360.39 | 11,602,389.71 | 10,1789,39.87 | 10,1789,39.87 |
| Goods and Services | 17,988,489.37 | 6,965,676.83 | 6,965,676.83 | 10,168,493.82 | 5,689,981.28 | 5,689,981.28 | 7,246,700.67 | 6,200,801.95 | 6,200,801.19 | 16,024,866.85 | 11,139,053.15 | 11,139,053.15 |
| CAPEX | 38,884,289.63 | 6,965,023.14 | 6,965,023.14 | 34,508,643.37 | 6,852,106.35 | 6,852,106.35 | 39,453,037.44 | 15,569,130.76 | 15,569,130.76 | 93,464,480.82 | 25,002,712.65 | 25,002,712.65 |
| Total | 60,400,000.00 | 17,374,283.50 | 17,374,283.50 | 49,380,000.00 | 17,092,666.67 | 17,092,666.67 | 54,173,000.00 | 21,769,932.71 | 28,639,292.34 | 121,091,737.38 | 36,141,765.80 | 36,141,765.80 |

Source: Finance Office, Dec. 2024, SMA

Appendix 6B: Capex Budget Performance Analysis

|  | Estimate |  | Release | Expenditure | Variance |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Unconstrained (A) | Constrained(B) | C | (D) | (A-B) | (B-C) | C-D |
| GOG | 7,324,071.22 |  |  |  |  |  |  |
| IGF | 550,000.00 | 2,530,720.00 | 836,814.00 | 836,814.00 | -1,980,720.00 | 1,693,906.00 | 0.00 |
| Donor | 63,909,321.93 | 86,066,552.81 | 21,396,651.00 | 21,396,651.00 | 22,157,231.81 | 64,669,901.81 | 0.00 |
| TOTAL | 71,783,393.10 | 88,597,272.81 | 22,233,465.00 | 22,233,465.00 | 20,176,511.81 | 66,363,807.81 | 0.00 |

Source: Finance Office, Dec. 2024, SMA

Appendix 6C: CAPEX budget allocation and implementation of active projects

| MULTI-YEAR CAPEX THROW FORWARD |  |  | MTBF ENVELOPE |  | PERFORMANCE |  | DETAILS ON CAPITAL PROJECTS, 2024 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | PROJECT |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | AGE | ORIGINAL ESTIMATE |  | EXPENDITURE TO DATE | OUTSTANDING BALANCE | COMPLETION STATUS |  |  |  | LAND ACQUISITION AND RESETTLEMENT |
|  | ANNUAL ESTIMATE | ANNUAL ESTIMATE | ANNUAL CEILING 2025 2024 |  |  |  | CODE | NAME |  |  | REVISED COST |  |  |  |  | TIME OVERRUNS | COST OVERRUN |  |
|  |  |  |  |  | APPROVED/RELEASED | EXPENDITURE |  |  |  |  |  |  |  | % | Pictures |  |  |  |
|  | 57,540,472.86 | 86,066,562.81 | 57,540,472.86 | 86,066,552.81 | 21,396,651.00 | 2,139,651.00 |  |  |  |  |  |  |  |  |  |  |  |  |
| 2022-2025 | 2025 | 2024 | 2025 | 2024 | 2024 | 2024 | 3113110 | CONSTRUCTION OF 2NO. MECHANIZED BOREHOLE WITHIN THE SUAME MUNICIPALITY | KRONUM/TAR KWA MAAKRO | 149,985.75 |  | 0.00 | 149,985.75 | 20% |  | - | - | The Local chiefs and Elders lease lands to the Assembly |
| GOG |  |  |  |  | 7,324,071.22 | 7,324,071.22 | 2210603 | PAINTING OF 1NO. 2-STOREY CLINIC FACILITY AT SUAME MAGAZINE | SUAME MAGAZINE | 149,961.00 |  | 149,961.00 | 0.00 | COMPLETED AND IN USE |  | - | - | The Local chiefs and Elders lease lands to the Assembly |
| IGF |  |  |  |  | 550,000.00 | 550,000.00 | 3111251 | CONSTRUCTION OF FENCE WALL FOR KWAPRA AT KWAPRA | KWAPRA | 449,979.00 |  | 384,531.00 | 65,448.00 | ON-GOING AT 75% COMPLETE |  | - | - | The Local chiefs and Elders lease lands to the Assembly |
| DONOR |  |  |  |  | 63,909,321.93 | 63,909,321.93 | 3111354 | CONSTRUCTION OF 9NO. LOCKABLE STORES AT ABOUHIA MARKET | ABUOHIA | 549,886.40 |  | 501,601.40 | 48,285.00 | ON-GOING AT 80% COMPLETE |  | - | - | The Local chiefs and Elders lease lands to the Assembly |
| Total |  |  |  |  | 7,783,393.15 | 7,783,393.15 | 3111353 | REHAILITATION OF 1NO.10-SEATER W/C TOILET FACILITY AT BREMAN M/A SCH. | BREMAN CLUSTER OF SCHOOLS | 219,341.00 |  | 219,341.00 | 0.00 | COMPLETED AND IN USE |  | - | - | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 3111201 | DEMOLITION AND RECONSTRUCTION OF BEDROOMS FACILITY FOR THE CONSTRUCTION VAMED HOSPITAL ACCESS ROAD AT ANOMAGYE | ANOMNAGYE | 250,608.50 |  | 250,608.50 | 0.00 | COMPLETED AND IN USE |  | - | - | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 2210603 | PAINTING OF 3-STOREY SUAME MUNICIPAL ASSEMBLY'S OFFICE BLOCK | SUAME | 350,165.00 |  | 350,165.00 | 0.00 | COMPLETED AND IN USE |  | - | - | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 3111201 | REHABLITATION OF KWAPRA HEALTH CENTER | KWAPRA | 543,592.86 |  | 516,412.17 | 27,180.69 | COMPLETED AND HANDED OVER |  | - | - | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 3111354 | CONSTRUCTION OF 60NO. LOCKABLE SHOPS FOR SUAME MUNICIPAL ASSEMBLY AT OLD SUAME MARKET | OLD SUAME | 5,045,735.75 |  | 5,061,639.08 | 15,903.33 | COMPLETED AND IN USE |  | - | - | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 3111354 | CONSTRUCTION OF STORE TYPE ‘E1’ 40, STORE TYPE ‘D1’ 32 UNIT, EXTERNAL WORKS AND 110M OF ROAD WITH DRAINAGE SYSTEM | KROPO | 8,232,994.13 |  | 7,511,625.01 | 721,369.12 | COMPLETED AND IN USE |  | - | - | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 3111354 | CONSTRUCTION OF POLICE POST/FIRST AID BLOCK AND CONSTRUCTION OF STORE TYPE ‘C7’ | KROPO | 4,796,919.62 |  | 4,359,367.66 | 437,551.96 | COMPLETED AND IN USE |  | - | - | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 3111354 | CONSTRUCTION OF 2-STOREY 8NO. STORES AND WASHROOM, 4-UNITS (40NO). STALL (TYPE E), 1UNITS (20NO). STALL (TYPE C), 1-UNIT (5NO). STALL (TYPE D), DEMOLITION AND EXTERNAL WORKS | KROPO | 4,360,128.18 |  | 3,990,607.93 | 369,520.25 | COMPLETED AND IN USE |  | - | - | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 3111353 | REHABLITATION OF 1NO. 20-SEATER WC FACILITY AT KRONUM CLUSTER OF SCHOOLS | KRONUM | 199,952.00 |  | 199,952.00 | 0.00 | COMPLETED AND IN USE |  | - | - | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 3111353 | REHABLITATION OF 1NO. 20-SEATER WC FACILITY AT KRONUM CLUSTER OF SCHOOLS | KRONUM | 198,202.00 |  | 198,202.00 | 0.00 | COMPLETED AND IN USE |  | - | - | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 3111363 | CONSTRUCTION OF 6M HEIGHT X 0.45M WIDTH: 48M LONG RETAINING WALL | OLD SUAME | 543,592.86 |  | 555,320.70 | -11,727.84 | COMPLETED AND IN USE |  | - | - | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 3111356 | CONSTRUCTION OF 1NO. 3-UNITS CLASSROOM BLOCK WITH OFFICES AND STORES | BREMAN CLUSTER OF SCHOOLS | 702,703.50 |  | 557,887.39 | 144,816.11 | ON-GOING AT 80% COMPLETE |  | - | - | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 3111256 | CONSTRUCTION OF 1NO. 3-STOREY 12-UNIT CLASSROOM BLOCK WITH ANCILLARY FACILITIES & 16 SEATER WC TOILET FACILITY (PHASE 1 - 6UNIT CLASSROOM BLOCK WITH ANCILLARY FACILITIES & 8SEATER WC TOILET FACILITY OF THE GROUND FLOOR) AT ST, JOSEPH PRIMARY SCHOOL, ANOMANGYE NKWANTA | ANOMNAGYE NKWANTA | 648,013.30 |  | 600,930.20 | 47,083.10 | COMPLETED AND IN USE |  |  |  | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 3111255 | CONSTRUCTION OF 1NO. 2-STOREY OFFICES AND LIBRARY & ICT CENTRE WITH MECHANIZED BOREHOLE AT SUAME M/A PRIMARY SCHOOL (PHASE 1 - GROUND FLOOR) | SUAME | 854,257.06 |  | 813,528.15 | 40,728.91 | COMPLETED AND IN USE |  | - | - | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 3111256 | CONSTRUCTION OF 1NO. 2-STOREY 6-UNIT CLASSROOM BLOCK WITH ANCILLARY FACILITIES AT BREMAN | SUAME | 749,775.87 |  | 639,550.04 | 110,225.83 | COMPLETED AND IN USE |  | - | - | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 3111353 | CONSTRUCTION OF 1NO. 12-SEATER WATER CLOSET TOILET FACILITY WITH 1NO. MECHANIZED BOREHOLE AT BREMAN NKONTWIMA SATELITE MARKET | KRONUM | 438,324.85 |  | 438,324.85 | 0.00 | COMPLETED AND IN USE |  | - | - | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 3111354 | CONSTRUCTION OF 8NO. LOCKABLE STORES, 50NO. OPEN SHEDS AND 10SEATER WC TOILET FACILITY FOR PROPOSED MARKET AT ABOUHIA | ABUOHIA | 818,198.82 |  | 744,457.43 | 73,741.39 | COMPLETED AND IN USE |  |  |  | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 3111256 | CONSTRUCTION OF 1NO. 2-STOREY GYMNASIUM AND LIBRARY & ICT CENTRE WITH MECHANIZED BOREHOLE AT MAAKRO M/A SCHOOL (PHASE 1 - GROUND FLOOR) | MAAKRO | 803,847.08 |  | 727,282.62 | 38,278.03 | COMPLETED AND HANDED OVER |  |  |  | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 3111255 | CONSTRUCTION OF 1NO. 2-STOREY AMBULANCE BAY WITH OFFICES AT TARKWA-MAAKRO | TARKWAMAAKRO | 899,896.91 |  | 854,530.58 | 45,366.33 | COMPLETED AND HANDED OVER |  | - | - | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 3111354 | CONSTRUCTION OF 1NO. 2-STOREY 12-UNITS LOCKABLE STORES AT TARKWA-MAAKRO | TARKWAMAAKRO | 1,112,299.86 |  | 1,056,567.39 | 55,732.47 | COMPLETED AND HANDED OVER |  |  |  | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 3111255 | CONSTRUCTION OF 1NO. 3-STOREY MUNICIPAL EDUCATION DIRECTORATE AT SUAME M/A PRIMARY SCHOOL (PHASE 2 - FIRST FLOOR) | SUAME | 549,043.56 |  | 398,119.73 | 150,923.83 | COMPLETED AND IN USE |  |  |  | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 3111256 | CONSTRUCTION OF 1NO. 3-STOREY 18-UNIT CLASSROOM BLOCK WITH ANCILLARY FACILITIES & 24-SEATER WC TOILET FACILITES (PHASE 1- 6 UNIT CLASSROOM BLOCK WITH ANCILLARY FACILITIES & 8-SEATER WC TOILET FACILITIES AT THE GROUND FLOOR AT ADADIEM M/A PRIMARY SCHOOL | ADADIEM | 979,326.81 |  | 146,899.02 | 832,427.79 | ON-GOING AT 75% COMPLETE |  |  |  | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 31112214 | PROCURE AND MAINTAIN STREETLIGHTS | MUNICIPALITY WIDE | 99,400.00 |  | 99,400.00 | 0.00 | Procured and maintained |  |  |  | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 2210603 | MAINTAIN OFFICE BUILDING, FURNITURE AND VEHICLES |  |  |  |  |  | Office building maintained |  |  |  | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 3112206 | PROCURE 1NO. GENERATOR PLANT | SUAME | 101,000.00 |  | 101,000.00 | 0.00 |  |  |  |  | The Local chiefs and Elders lease lands to the Assembly |
|  |  |  |  |  |  |  | 2210108 | CONSTRUCTION OF FENCE WALL FOR KWAPRA HEALTH CENTRE | KWAPRA | 449,979.00 |  | 449,979.00 | 0.00 |  |  |  |  | The Local chiefs and Elders lease lands to the Assembly |

Source: MPCU-SMA, Dec. 2024, SMA

Annex 6D: Cumulative CAPEX thrown forward and MTBF Envelope, 2025 – 2027

| Item | Amount |
| --- | --- |
| Capex throw Forward | 30,003,255.10 |
| MTBF (Ceilings) | 26,217,545.60 |
| Variation | 3,785,709.55 |

Annex 6E: Amount of capital envelope spent on active projects

| Sector | Capital envelope amount | Amount spent on rollover projects | Amount spent on new projects |
| --- | --- | --- | --- |
| Economic | 7,063,536.68 |  |  |
| Social | 4,584,787.30 |  |  |
| Environment | 30,125,870.39 |  |  |
| Governance | 170,501.27 |  |  |
| Total |  |  |  |

Annex 6F: Estimated Cost and Cost overruns of Active Projects

| Sector | Total contract sum GH₵ | Revised contract sum | Cost overrun | Actual payment | Outstanding Balance | % Work Done |
| --- | --- | --- | --- | --- | --- | --- |
| Economic Sector 1.Construct 8No. Lockable Stores, 50No. open sheds and 12-Seater WC Toilet Facility for proposed market 2. Construct 1No. 2 Storey 12-Unit lockable stores 3. Relocate traders for the redevelopment of Old Suame Market 4. Construct 60No. lockable shops at Old Suame Market | 7,063,536.68 818,198.82 1,112,299.86 87,302.25 5,045,735.75 | NIL NIL NIL NIL | NIL NIL NIL NIL |  |  | 100% 80% 100% 59.45% |
| Social Sector 1.Construct 1No. 2Storey Ambulance Bay 2. Construct 1 No. 3 Storey 18 Unit Classroom Block with ancillary facilities & 24-Seater W/C Toilet Facilities (phase 1-6 unit Classroom Block with ancillary facilities & 8-seater WC Toilet Facilities at the Ground Floor. 3. Construction of 1No. 3 Storey 12 Unit classroom block with ancillary facilities and 16-Seater WC Toilet Facilities (phase 1-6-Unit classroom block with ancillary facilities and seater WC Toilet facilities of the Ground Floor) 4. Construct 1No. 2 Storey 6Unit Classroom Block with ancillary facilities 5. Rehabilitate Boreholes | 4,584,787.30 899,896.91 979,324.61 72,718.39 749,775.87 3850.00 | NIL NIL NIL NIL NIL | NIL NIL NIL NIL NIL | NIL NIL NIL NIL NIL |  | 66% 45% 100% 100% 100% |
| Environmental/Infrastructure/Human Settlement 1.construct 1No. 12-Seater Water Closet Toilet Facility with 1No. Mechanized Borehole 2. Construct 1No. 3 Storey Municipal Education Directorate at Suame M/A Primary School (Phase 2-First floor) 3. Complete 1No. 2 Storey Court Building with mechanized Borehole at Breman Central (phase 1-Ground floor) 4.Construct 1No. 2 Storey Gymnasium and Library &ICT center with mechanized borehole (phase 1- ground floor) | 30,125,870.39 438,324.85 549,043.56 208,050 803,847.08 | NIL NIL NIL NIL | NIL NIL NIL NIL | NIL NIL NIL NIL |  | 100% 81% 100% 80% |
| 5. Construct 1 No 3 Storey offices and library & ICT center with mechanized borehole (Phase 1- Ground floor) | 854,257.06 | NIL | NIL | NIL |  | 100% |
| 6. Construction of Police Post/Fist Aid Block and construction of store type C 7 | 4,545,597.12 | NIL | NIL | NIL |  | 98% |
| 7. Construct 2 Storey 8 No stores and washroom, 4-unit (40 No). Stall (Type E), 1-Units (20No). Store (Type C), 1-Unit (5No), Stall (Type D), Demolition and External Works | 4,161,704.18 | NIL | NIL | NIL |  | 95% |
| 8. Construct Store Type “E1” 40, Store Type “D1” 32 Unit, External Works and 1 10 m of Road Drainage System | 6,398,859.29 | NIL | NIL | NIL |  | 60% |
| 9. Construction of 60 No. Lockable Shops at old Suame Market | 5,045,735.75 | NIL | NIL | NIL |  | 59.45% |
| 10. Construct 900 mm Diameter Pipe Storm Drain | 196,793.34 | NIL | NIL | NIL |  | 100% |
| 11. Construct Storm drain at kyerase |  | NIL | NIL | NIL |  |  |
| 12. Complete reinforced concrete storm drains with box and pipe covert footbridges at Kronum Abuohia | 2,615,442.12 | NIL | NIL | NIL |  | 100% |
| 13. Procure and maintain street lights | 169,889.40 | NIL | NIL | NIL |  | 100% |
| 14. Potholes Patching and Filling Works at Adadiem and selected Roads | 148,740.00 | NIL | NIL | NIL |  | 100% |
| 15. Carry out emergency repair Works on covert at Abuohia at Kronum kyerase (Adonko) | 75,799.00 | NIL | NIL | NIL |  | 100% |
| 16. Reshape Kwapra New life school | 198,828.00 | NIL | NIL | NIL |  | 100% |
| 17. Complete 1No. 12-Seater WC Toilet at Abuohia | 348,344.76 | NIL | NIL | NIL |  | 100% |
| 18. Acquire lands for projects | 2,600,000.00 | NIL | NIL | NIL |  | 62% |
| 19.Complete reinforced concrete storm drains with box and pipe culverts at old Suame | 706,614.88 | NIL | NIL | NIL |  | 100% |
| 20. Maintain pedestrian footbridges/ Walkways | 60,000.00 | NIL | NIL | NIL |  | 100% |
| Governance Sector 1.Supply and install office equipment 2. Procure office furniture and other consumable 3. Maintain Official Vehicles | 170,501.27 112,652.80 47,848.47 10,000.00 | NIL NIL NIL | NIL NIL NIL | NIL NIL NIL |  | 100% 100% 100% |

Annex 7a: Update on Critical Development and Poverty Issues, 2024

| Critical Development and Poverty Issues | 2024 Allocation GH¢ | Actual Receipt 2024 (GH¢) | No. of beneficiaries |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Baseline 2023 | Targets 2024 | Actuals 2024 |
| Free SHS Programme | - | - | 0 | 0 | 1,645 |
| Ghana School Feeding Programme | - | - | 0 | 6,000 | 6,505 |
| Capitation grants | - | 50,379.16 | 23,769.52 | 60,000.00 | 50,379.16 |
| National Health Insurance Scheme | - | - | 2,173,32 | - | - |
| Livelihood Empowerment Against Poverty (Leap) Programme | 139,648.00 | 96,272.00 | 95 | 90 | 90 |
| Planting for Food and Jobs Programme | 0 | 0 | 0 | 0 | 0 |
| Modernizing Agriculture in Ghana | 59,098.63 | 0 | 59,098.63 | 0 | 0 |

Source: SMA, MPCU DEC. 2024

Annex 7b: Staff Strengths of MMDAs

| Departments | Requirements |  | Actual | % Covered | Training Required |
| --- | --- | --- | --- | --- | --- |
|  | Minimum | Maximum | 2024 |  |  |
| Central Administration | 77 | 114 | 87 | 112.9% | Managing work place conflict and Co-ordination skill |
| Human Resource | 3 | 4 | 5 | 166.67% | Occupational Health and Safety |
| Physical Planning | 10 | 15 | 4 | 40% | Protocol of the Service |
| Agriculture | 19 | 29 | 10 | 52.63% | Train Staff on Web Based M& E report writing and conflict Management at workplace |
| Social Welfare and Community Development | 7 | 9 | 12 | 171.43% | Protocol of the Service (Benefit) |
| Works | 30 | 41 | 9 | 30% | Project Management, communication skills, Team building skills and the Protocol of Service |
| Total | 146 | 212 | 127 | 86.99% |  |

Source: SMA MPCU, DEC. 2024

| Name or type of the Capacity Development | Venue/Location | Purpose of the Programme | Source of funding | Target group | Facilitators | No. of beneficiaries |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Total | Male | Female |
| Occupational Health and Safety | Assembly’s Conference Hall | Sensitized staff on safety at work | DACF | Management | MCD/HRMD | 40 | 20 | 20 |
| Protocol of the Service | Assembly’s Conference Hall | To enhance staff Knowledge | DACF | All Staff | HRMD | 96 | 56 | 40 |

Annex 7c: Capacity Development

Source: SMA MPCU, DEC. 2024

Annex 7d: Logistics Analysis

| Required | Required | Actual | Remarks |
| --- | --- | --- | --- |
| Computers | 35 | 23 | Additional 12 computers are required for smooth administration operations. |
| Printers | 40 | 25 | Additional 15 computers are required for smooth administration operations. |
| Projectors | 5 | 2 | Additional 3 computers are required for smooth administration operations. |
| Office Space | 68 | 49 | Additional Office Space are needed for effective job satisfaction |
| Vehicle | 14 | 10 | Additional 4 Vehicles are required for official duties. |

Source: SMA MPCU, DEC. 2024

# Annex 8: Update on Evaluations conducted

| Name of Evaluation | Programme | Consultant/ Resource Persons Involved | Methodology used | Findings | Recommendations |
| --- | --- | --- | --- | --- | --- |
| Terminal evaluation | Greater Kumasi Metropolitan Area Sanitation and Water Project | Department of Planning, KNUST | Beneficiaries Survey | The project had improved contact hours for girl child and reduced Gender Based Sexual harassment and abuse among girl child | Future institutional toilet facilities should make provisions for girls changing rooms to cater for girls during their menstrual cycles to avoid a situation where girls go home during such periods and some never return to school thereby affecting the contact hours |

Source: SMA MPCU, DEC. 2024

Annex 9: Update on Participatory M&Es Conducted

| Name of the PM&E Tool | Policy/Programme/Project involved | Consultant or resource persons involved | Methodology used | Findings | Recommendations |
| --- | --- | --- | --- | --- | --- |

Source: SMA MPCU, DEC. 2024